## Slide 1
139788 Step 3 — Dead-leg and hold-up retrofit
Demo: Option 1 Pre-PPQ and PPQ: Option 2 Commercial: Option 3
All four steps handle process material.
Option | What it covers | Potential risk | Mitigation | After mitigation | Due
1 | Dead legs outside the 2D/3D criterion, diaphragm valves that are not self-draining, and non-BPE piping stay in place. | Hold-up can degrade material, support microbial growth, or cause cross-contamination. Flush, drain, purge, and disassembly after each use are not defined. | After each system transfer, flush or clean with process solvent, supported by bioburden data. Define those steps in the procedures. | Low | Nov 5, 2026
2 | Rebuild piping and vessels with hygienic T-valves and 3D short-outlet tees. Control dead legs, slope, and drainability. Reserve CIP tie-in valves. | New change control, with a concern for product quality. Pre-use and post-use steps may still be insufficient. | Qualify the modified piping. Define the operating and cleaning sequence and update the records. | Low | Feb 6, 2027
3 | Add clean-in-place on the Option 2 piping, including slope, drainage, dead-leg removal, and pre-use flush, cleaning, disinfection, and purge. | The design may be incomplete, and the CIP sequence and controls may be incomplete. | Qualify the system as a whole. Update the SOP and bring the requirements into routine use. | Low | 5 months after Option 2
Process step | Demo | Pre-PPQ | PPQ | Commercial
Preparative buffer preparation | Option 1 | Option 2 | Option 2 | Option 3
Preparative chromatography | Option 1 | Option 2 | Option 2 | Option 3
TFF | Option 1 | Option 2 | Option 2 | Option 3
Precipitation | Option 1 | Option 2 | Option 2 | Option 3
139788 Step 3 · Dead-leg and hold-up retrofit