## Slide 1
139788 · STEP 3
Dead-leg and hold-up retrofit
Schedule for the three options, and where each one applies.
Asymchem · Client review · October 2026

## Slide 2
Demo uses Option 1. Pre-PPQ and PPQ use Option 2.
Commercial manufacture uses Option 3. All four steps handle process material.
Process step | Demo | Pre-PPQ | PPQ | Commercial
Preparative buffer preparation | Option 1 | Option 2 | Option 2 | Option 3
Preparative chromatography | Option 1 | Option 2 | Option 2 | Option 3
TFF | Option 1 | Option 2 | Option 2 | Option 3
Precipitation | Option 1 | Option 2 | Option 2 | Option 3
139788 Step 3 · Dead-leg and hold-up retrofit
2 / 5

## Slide 3
Option 1: procedural control by November 5, 2026.
The piping stays as it is. The control is how the line is used and cleaned.
POTENTIAL RISK
Hold-up in the piping can degrade the material, support microbial growth, or cause cross-contamination. The flush, drain, purge, and disassembly required after each use are not defined.
WHAT REMAINS
Some piping does not meet the 2D/3D dead-leg criterion.
Some diaphragm valves do not meet the self-draining requirement.
Some piping is not ASME BPE piping.
WHAT WE WILL ADD
After each system transfer, flush or clean with process solvent. Bioburden data support this step.
Write the flush, drain, purge, and disassembly requirements into the procedures.
RESIDUAL RISK
Low, once the tighter procedural controls are in place.
DUE
November 5, 2026
139788 Step 3 · Dead-leg and hold-up retrofit
3 / 5

## Slide 4
Option 2: piping retrofit complete by February 6, 2027.
This is the configuration for Pre-PPQ and PPQ.
THE RETROFIT
Rebuild the piping and vessels with hygienic T-valves and short-outlet tees meeting the 3D criterion.
Control dead legs, slope, and drainability.
Leave valves for a later CIP connection.
RISK AND THE RESPONSE
This is a new change control. The concern is an effect on product quality, and pre-use and post-use steps that are not yet sufficient.
Qualify the modified piping. Define the operating and cleaning sequence, and update the records.
RESIDUAL RISK
Low, with the modified hardware and the revised sequence.
DUE
February 6, 2027
139788 Step 3 · Dead-leg and hold-up retrofit
4 / 5

## Slide 5
Option 3 adds CIP, five months after Option 2.
This is the configuration for commercial manufacture. It is built on the Option 2 piping.
WHAT CIP ADDS
Clean-in-place on the retrofitted piping.
Slope, drainage, and removal of dead legs.
Pre-use flush, cleaning, disinfection, and purge, all done in place.
RISK AND THE RESPONSE
The design may be incomplete, and the CIP sequence and controls may be incomplete.
Qualify the system as a whole. Update the SOP and bring the requirements into routine use.
RESIDUAL RISK
Low, with the revised piping and the CIP cycle.
DUE
5 months after
Option 2
139788 Step 3 · Dead-leg and hold-up retrofit
5 / 5