## Slide 1
139788 Step 3 Piping Dead Legs and Residue: Retrofit Timeline
Option | Description | Potential Risk | Mitigation Plan | Residual Risk | Due Date
Option 1 | 20 locations do not meet the 2D/3D dead-leg requirement, and 11 diaphragm valves are not self-draining. Some lines are not BPE tubing. | Residue in the lines reduces product yield; residual material may degrade or support microbial growth. No defined requirements for rinsing, draining, purging or disassembly after each use of the lines. | After each material transfer, add a process-solvent rinse so that the residue is a non-growth-promoting medium. Update the operating and cleaning procedures to define rinsing, draining, purging and disassembly requirements. | Low (with enhanced procedural controls) | 10/15/2026
Option 2 | Retrofit lines and tanks with zero-dead-leg tee valves and short-outlet (3D) tees to control dead legs, slope and drainage. | New change control; impact on product quality must be assessed. Pre-use and post-use operations not sufficiently defined. | Qualify the retrofitted lines. Define the operating and cleaning procedures and update the related forms. | Low (with retrofitted hardware and defined procedures) | 12/27/2026
Option 3 | Retrofit lines and tanks with zero-dead-leg tee valves and GMP block valves to control dead legs, and install a CIP system for cleaning in place. | Inadequate design. Inadequate control of the CIP program. | Qualify the equipment as a whole. Achieve proper slope and full drainage and eliminate dead legs. Provide pre-use flushing, cleaning, sanitization and purging, with full CIP capability. Update SOPs to incorporate these requirements into routine operation. | Low (with improved piping hardware and CIP program) | 04/25/2027
Process Step | Service | Demo | Pre-PPQ | PPQ | Commercial
Preparative Solution Prep | Process materials | Option 1 | Option 2 | Option 2 | Option 3
Preparative Purification | Process materials | Option 1 | Option 2 | Option 2 | Option 3
TFF | Process materials | Option 1 | Option 2 | Option 2 | Option 3
Precipitation | Process materials | Option 1 | Option 2 | Option 2 | Option 3