ELI LILLY AND ASYMCHEM

API External Manufacturing (APIEM)

Gap Assessment and Risk Assessment

For Technology Transfer

| Document Title | Gap Assessment / Risk Assessment for Technology Transfer of LSN4182928 / ASYM-140021 from Full Scale Non-saleable Batch to PPQ Batches at Asymchem Life Science (Tianjin) Co., Ltd., |
| --- | --- |
| Document ID | GA-140021-0301.01 |
| Product / Lilly ID | LSN4182928 / ASYM-140021 |
| Sending Site (Current Process) | Asymchem Life Science (Tianjin) Co., Ltd |
| Receiving Site (CMO) | Asymchem Life Science (Tianjin) Co., Ltd |
| Commercialization Phase | Process Performance Qualification / Commercial production |

l

Approval and Signatures

This document requires review and approval by the roles listed below prior to commencement of process validation or PPQ activities at the Asymchem Life Science (Tianjin) Co., Ltd, (No.265, South Avenue, Binhai New Area TEDA, Tianjin, 300462, P.R. China) (Referred to as TJ4). Approval is required from both sending and receiving site representatives. Data Integrity review is also required.

| Prepared by |  |  |
| --- | --- | --- |
| Yu Zhang (Associate Director, CMMD) | Signature &Date |  |
| Reviewed by |  |  |
| Tingquan Yang (Senior Director, CMMD) | Signature &Date |  |
| Yongle Liu (Director, Dept. of Analytical Research and Development) | Signature &Date |  |
| Haini Wang (Senior Director, QC) | Signature &Date |  |
| Zhongyao Zhang (Director, Production) | Signature &Date |  |
| Lu Li (Director, QA) | Signature &Date |  |
| Approved by |  |  |
| Mingyang Yang (Executive Director, QA) | Signature &Date |  |

–  This document is reviewed and approved by Eli Lilly and Company. Refer to signature page for EDMS signatures and dates for Eli Lilly and Company approval.

Version History

| Version | Date | Summary of Changes |
| --- | --- | --- |
| 01 | The last signature date is defined as the effective date | The first version |

Abbreviations and Definitions	6

1. Report Summary	8

2. Scope and Purpose	9

3. Gap Assessment / Risk Assessment	11

3.1 Process Chemistry	11

3.2 Process Changes 	12

3.3 Process Equipment	13

3.4 Specifications and Analytical Methods 	18

3.4.1 Raw Material Specifications	18

3.4.2 In-Process Control (IPC) Items and Methods	24

3.4.3 Analytical Methods	26

3.5 Cleaning Validation	33

3.6 Technology Transfer Gap Assessment (by Area)	34

4. Summary Risk Mitigation / Action Plan	49

5. Raw Material Supplier Information	54

6. Personnel	55

7. Cleaning	55

8. Storage and Handling Conditions	55

9. Packaging Materials	55

10. Conclusion	56

11. References	57

12. Appendix I Risk Mitigation Measures/Action Plan Tracking Table	58

# Abbreviations and Definitions

The following abbreviations and definitions apply throughout this document.

| Abbreviation / Term | Definition |
| --- | --- |
| APIEM | API External Manufacturing (Eli Lilly) |
| AR | Analytical Research lab |
| cGMP | Current Good Manufacturing Practice |
| CM | Contract Manufacturer |
| PLC | Programmable Logic Controller |
| DCM | Dichloromethane |
| DIC | N,N'-Diisopropylcarbodiimide |
| DIPEA | Ethyldiisopropylamine |
| DMF | N,N-Dimethylformamide |
| DS | Drug Substance |
| EHS | Environment, Health and Safety |
| EA | Ethyl acetate |
| ESA | Equipment Suitability Analysis |
| Fmoc | 9-Fluorenylmethyloxycarbonyl |
| IPAc | Isopropyl acetate |
| IPC | In-Process Control |
| LDPE | Low density polyethylene |
| LOD | Loss on Drying |
| MOC | Material of Construction |
| MOR | Master Operation Record |
| MeOH | Methanol |
| MTBE | Methyl tert-butyl ether |
| Oxyma | Ethyl cyano(hydroxyimino)acetate-2-oxime |
| OEB | Occupational exposure band |
| OOS | Out of Specification |
| PFD | Process Flow Document |
| PHA | Process Hazard Analysis |
| PyBOP | Benzotriazol-1-yl-oxytripyrrolidinophosphonium hexafluorophosphate |
| PPQ | Process Performance Qualification |
| QA | Quality Assurance |
| QC | Quality Control |
| RA | Risk Assessment |
| RSM | Registered Starting Material |
| SPPS | Solid Phase Peptide Synthesis |
| SS | Stainless Steel |
| TS/MS | Technical Services / Manufacturing Science |
| TFA | Trifluoroacetic acid |
| UPLC | Ultra High-Performance Liquid Chromatography |
| VMP | Validation Master Plan |
| 2-CTC | 2_Chlorotrityl Chloride Resin |
| 2-MeTHF | 2-Methyltetrahydrofuran |

# 1. Report Summary

Title of Report

Gap Assessment / Risk Assessment for Technology Transfer of LSN4182928 / ASYM-140021 from Full Scale Non-saleable Batch to PPQ Batches at Asymchem Life Science (Tianjin) Co., Ltd.,

Lilly Number/ Name

LSN4182928

Abstract

This report provides the detailed gap assessment / risk assessment to meet the requirements of the LSN4182928 / ASYM-140021 technology transfer. The assessment documents all identified gaps or differences across the scope areas, as well as the associated risks of these gaps on drug substance quality. The purpose of this assessment is to evaluate the readiness of the manufacturing process, analytical methods, equipment, facilities, utilities, personnel, contamination control strategy and quality systems for execution of PPQ activities associated with LSN4182928. The assessment further verifies that technology transfer activities, process changes, risk mitigations and prerequisite validation activities are appropriately controlled such that process performance, product quality and patient safety are not adversely impacted. No changes are made to the participant team, synthetic process route, raw material supplier information, cleaning procedures, storage and handling conditions, and packaging materials. Only the following optimization items are identified, which have no impact on commercial manufacturing and product Critical Quality Attributes (CQAs): - The specifications of raw materials have been refined and tightened to enable enhanced product quality control. The overall risk level of this change is assessed as low. - For Step 1： - The in-process confirmation of resin adherence and the corresponding DMF wash operation at other time points during the reaction are removed. No peptide resin wall adhesion has been observed at full-scale production. - The visual confirmation step for amino acid complete dissolution is eliminated. The operation duration will be executed strictly per the dissolution time established from engineering batches to ensure operational consistency. - A flow meter with fixed-rate dosing control and extension piping are implemented for iodine addition, to strengthen process operational control and dosing accuracy. - For Step 2: - The original defined cleavage temperature range is 10–20 °C. To ensure operational consistency and guarantee cleavage efficiency, the cleavage start time is revised to commence timing once the target temperature of 15 °C is reached. - The post-cleavage rinse volume is increased from 5 volumes to 8 volumes. The original wash volume was insufficient and resulted in poor agitation performance; the increased volume ensures sufficient resin washing and reduces yield loss. - After neutralization and phase separation, the organic phase is transferred to the concentrator, while the aqueous phase is held for waste disposal. A small portion of organic phase (~20–50 L) was found entrained in the aqueous phase during the waste discharge step (with a long holding interval). Given the increased wash volume and minor organic phase entrainment, the process is revised to two-stage phase separation and batch-wise concentration. - The thermowell of the cleavage reactor is replaced to improve mixing efficiency and enhance process yield. - For Step 3: - Prior to crystallization, concentration with solvent stripping is performed to reduce water (KF) and acetonitrile content. Engineering batch data showed KF values of approximately 5% after concentration to target volume (acceptance criterion: ≤ 2.5%). An additional 2-methyltetrahydrofuran (2-MeTHF) solvent chase step followed by in-process sampling and testing is planned, to avoid repeated out-of-spec testing, save analytical resources and improve manufacturing efficiency. - Originally, Step 3 shared n-heptane storage tank TJ4S-1213-Tr06 (for controlled-rate feeding) with Step 2. A new dedicated storage tank TJ4S-1213-Tr07 is added exclusively for Step 3 to improve production efficiency. - Equipment modification for PV batches: - Prepare solution tank TJ4S-1213-AT09: Add sight glass on transfer line; remove DP level gauge. - TJ4S-1213-R07& TJ4S-1213-R03& TJ4S-1213-R14: In-line conductivity meter validation; Radar level gauge validation. - Unstable TJ4S-1213-R12 to TJ4S-1213-R14 transfer flow meter; replace & add standby dosing pump; implement agitator-pump interlock; add bypass; coordinate program issue. - In-line conductivity meter validation; Radar level gauge validation. - Fabricate TJ4S-1213-R14 corrosion-resistant piping; equip dosing pump, ball valve, Hastelloy flow meter for HCl transfer; develop dosing control program; sloped dead volume piping, add output port. - In-line conductivity meter validation; Radar level gauge validation. - Store n-Heptane tankTJ4S-1213- Tr06& TJ4S-1213- Tr07& TJ4S-1212-AT01 :Add heating for n-heptane line with TCU ,Add tank thermometer to DCS. - TJ4S-1213-R03 and TJ4S-1213-R06: Spray ball modification; supplementary spray coverage validation to follow. - TJ4S-1212-FD01& TJ4S-1212-FD02& TJ4S-1212-FD03: Replace nitrogen flow meters with 0~60m³/h range to meet 10~40m³/h process requirement; Optimize DCS level & volume display for waste tanks (dead volume marked). All the changes described above have no impact on product CQAs, with an overall assessed risk level of low.

# 2. Scope and Purpose

The purpose of this report is to document the detailed gap assessment / risk assessment for the technology transfer of LSN4182928 / ASYM-140021 between full scale non-saleable batch and PPQ batches as well as the following commercial manufacturing at TJ4. The scope of this assessment includes evaluation of process readiness, analytical readiness, equipment suitability, contamination control readiness, validation readiness, quality system readiness, material readiness and completion status of prerequisite PPQ activities.

Table 1: Gap Assessment Team

The cross-functional team shown below has reviewed the ASYM-140851 and process from the sending site and receiving site.

| Role | Sending Site (Asymchem) | Receiving Site (Asymchem) |
| --- | --- | --- |
| Process chemist | Yu Zhang Associate Director , CMMD | Yu Zhang, Associate Director , CMMD |
| Technical Reviewer | Tingquan Yang, Senior Director, CMMD | Tingquan Yang, Senior Director, CMMD |
| Process Engineering | Zhongyao Zhang, Director , Production | Zhongyao Zhang, Director , Production |
| Operations | Yue Sun, Associate Director , Production | Yue Sun, Associate Director , Production |
| Quality Assurance | Lu Li, Associate Director, QA | Lu Li, Associate Director, QA |
| Laboratories (QC) | Haini Wang, Senior Director, QC | Haini Wang, Senior Director, QC |
| Dept. of Analytical Research and Development (ARD) | Yongle Liu, Director, ARD | Yongle Liu, Director, ARD |

Table 2: Risk Scoring Table — Severity of Harm Impact on LSN4182928 / ASYM-140021 Quality

Risk classification follows the scoring scale below. The scoring is based on impact to the quality of LSN4182928 / ASYM-140021. Risk classification assumes no action or mitigation has been implemented.

| Risk Level | Severity of Harm — Impact on the quality of LSN4182928 / ASYM-140021 |
| --- | --- |
| Low | No or low correlation with CQA based on available data or extensive prior knowledge. |
| Medium | Potentially low correlation with CQA based on prior/scientific knowledge and failure of acceptance criteria is not expected; however, data is not available or studies are ongoing. |
| High | Parameter has strong correlation with CQA, may cause exceedance of CQA limit, either based on experimental data or prior/scientific knowledge. |

The summary table in Section 4 provides the consolidated action plan with owners and milestones. Technical risks, mitigations and completion milestones will also be agreed during project Manufacturability Reviews.

# 3. Gap Assessment / Risk Assessment

This section  identifies differences or gaps to be addressed during transfer of this LSN4182928 / ASYM-140021 to the Asymchem TJ4. For each area, the sending site status is documented, any challenges/gaps/differences at Asymchem TJ4 are described, a risk ranking is assigned per Table 2, and a mitigation plan or action is proposed.

## 3.1 Process Chemistry

3.1.1 The synthetic scheme for ASYM-140851 is shown below.

Scheme 1 Synthetic scheme for the ASYM-140851

The synthetic route of ASYM-140851 adopted at the Asymchem TJ4 remains unchanged. The compound ASYM-140851 is an in-process product for the synthesis of LSN4182928 /ASYM-140021, which is synthesized via solid-phase synthesis, with 2-CTC Resin as the starting material; Other amino acids are sequentially coupled via coupling reactions including Fmoc-Gly-OH, Fmoc-L-Thr(tBu)-OH, Fmoc-L-Ala-OH*H2O, Fmoc-L-Cys(Trt)-OH, Fmoc-L-Asn(Trt)-OH, Boc-L-Glu-OtBu. After the synthesis of the SPPS peptide fragment through solid phase, on resin disulfide is formed by removing the Trt group with the iodine oxidation. Also, the coupling reagents, namely Oxyma, PyBOP, DIC and DIPEA, remain unchanged throughout technology transfer.

3.1.2 The synthetic scheme for the LSN4214882/ASYM-140852 is shown below.

Scheme 2, Synthetic scheme for LSN4214882/ASYM-140852

The intermediate Boc-L3-SS is obtained by soft cleavage (cocktail of TFA/DCM) from the 2-CTC resin.

3.1.3 The synthetic scheme for the LSN4182928 / ASYM-140021 is shown below.

Scheme 3, Synthetic scheme for LSN4182928 / ASYM-140021

Finally, a two-stage reaction (stage 1: linear peptide formed by the reduction of TCEP, stage 2: cyclization with diiodomethane) is conducted to generate dithioacetal bridge between 2#&7# cysteine.

3.2 Process Changes

Asymchem is pleased to present a development report detailing the optimized processes for Step1~3 in support of the 3rd campaign (API-8) PAR study and manufacture of LSN4182928/ASYM-140021.

3.2.1 The Process Changes for ASYM-140851(Step 1)

The changes documented  are grouped into five categories: (1) MOR documentation and GMP enhancements (Incident Log, dual-person verification, expanded pre-charging and visual-inspection checklists, and clarified roles and records), which do not alter process steps or parameters; (2) process parameter refinements (minimum dissolution, activation and mixing times, visual discharge/transfer endpoints, removal of the agitation-stop step, and formal CPP/NOR designation), each supported by the PAR study and full-scale batch experience and kept within demonstrated ranges;

On the basis of the PAR, risk

3.2.2 The Process Changes for LSN4214882/ASYM-140852 (Step 2)

There is no change in manufacturing scale. Process parameter adjustments are implemented due to unsatisfactory mixing performance, including agitation speed and rinse volume. The changes are based on the supplementary PAR study report. These parameter adjustments have no adverse effect on the quality of process intermediate LSN4214882/ASYM-140852 (Step 2).

Parameters will be revised based on the PAR study. Based on the PAR, risk assessments, full-scale batch and solvent-run evidence, the proposed changes will not adversely affect product CQAs, impurity profile, yield, cleaning, stability or PPQ success. The revised parameters and methods will be specifically monitored and trended across the three PPQ batches as a change effectiveness check. For details of related changes,  refer to Change-CPo140021-030202.01

3.2.3 The Process Changes for LSN4182928/ASYM-140021 (Step 3)

Process parameters remain unchanged, with no adverse effect on the quality of product LSN4182928/ASYM-140021 (Step 3).

Parameters will be revised based on the PAR study. Based on the PAR, risk assessments, full-scale batch and solvent-run evidence, the proposed changes will not adversely affect product CQAs, impurity profile, yield, cleaning, stability or PPQ success. The revised parameters and methods will be specifically monitored and trended across the three PPQ batches as a change effectiveness check. For details of related changes, refer to Change- Change-CPo140021-030303.01

3.3 Process Equipment

3.3.1 The process equipment for ASYM-140851 (Step 1)

The process equipment proposed for the PPQ campaign is listed below and compared with the Full Scale non-saleable batch equipment. The step 1 Equipment Suitability Analysis (ESA) have been completed and documented in Equipment Suitability Assessment Report < RA-140021030102.01>, in which all equipment suitability conclusion required for PPQ  have been clearly defined, and this document will be approved  prior to the PPQ batch.

Table 3: The Step 1 Process Equipment Gap Comparison

| Intended Purpose | Full Scale non-saleable batch Equipment Code | Capacity | MOC | PPQ Equipment Code | Capacity | MOC | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Peptide synthesis, Fmoc deprotection, Wash resin, Drying | TJ4S-1213-Sy16 | 3000L | Hastelloy | TJ4S-1213-Sy16 | 3000L | Hastelloy | No gap —the equipment is unchanged. The validated lower limit of jacket temperature for the solid-phase synthesis reactor is supplemented from -10 °C to -12 °C. |
| Activation tank | TJ4S-1213-Sy16-R01 | 1500 L | Stainless steel | TJ4S-1213-Sy16-R01 | 1500 L | Stainless steel | No gap — same equipment. |
| Storage of Prepared De-Fmoc Solution | TJ4S-1213-SPS01-AT01 | 3000 L | Stainless steel | TJ4S-1213-SPS01-AT01 | 3000 L | Stainless steel | No gap — same equipment. |
|  | TJ4S-1213-SPS01-AT02 | 3000 L | Stainless steel | TJ4S-1213-SPS01-AT02 | 3000 L | Stainless steel | No gap — same equipment |
| Iodine/DMF solution preparation | TJ4S-1213-AT09 | 500 L | Glass-lined | TJ4S-1213-AT09 | 500 L | Glass-lined | No gap — same equipment. |
| DIC/DMF solution preparation | TJ4S-1200-AT01 | 500 L | Hastelloy | TJ4S-1200-AT01 | 500 L | Hastelloy | No gap — same equipment |

Note: For the I₂/DMF transfer from preparation tank TJ4S-1213-AT01 to synthesis reactor TJ4S-1213-Sy16, a tantalum mass flow meter is added to the diaphragm metering pump, enabling real-time flow monitoring, closed-loop pump-speed control and immediate detection of blockage or deviation; the transfer path and the corrosion-resistant wetted materials remain unchanged, improving transfer-rate accuracy and oxidation total-exposure control with no adverse impact on PPQ success or product quality.

Conclusion: The equipment used for  Full scale non saleable batches and PPQ batches is identical, and its parameters meet process requirements. Reference the Equipment Suitability Assessment report (RA-140021030102.01<Equipment Suitability Assessment for ASYM-140851 (step 1)>).

3.3.2 The Process Changes for LSN4214882/ASYM-140852 (Step 2)

The process equipment proposed for the PPQ campaign is listed below and compared with the Full Scale non-saleable batch equipment. The Step 2 Equipment Suitability Analysis (ESA) and report are in preparation and will be completed by Asymchem prior to the step 2 PPQ campaign.

Table 4: The Step 2 Process Equipment Gap Comparison

| Intended Purpose | Full Scale non-saleable batch Equipment Code | Capacity | MOC | PPQ Equipment Code | Capacity | MOC | Comments / GAP Assessment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Cleavage&Rinse | TJ4S-1212-R07 | 2000 L | Glass-lined (mesh / membrane :Hastelloy) | TJ4S-1212-R07 | 2000 L | Glass-lined (mesh / membrane :Hastelloy) | Same equipment:To improve shear mixing efficiency, the thermowell will be replaced, followed by equipment re-validation and engineering re-assessment. . |
| Prepare neutralization solution, Neutralization, Ascorbic / NaCl solution preparation | TJ4S-1213-R07 | 12500 L | Glass-lined | TJ4S-1213-R07 | 12500 L | Glass-lined | No gap — same equipment. |
| Concentration, Wash, Precipitation | TJ4S-1213-R03 | 5000 L | Glass-lined | TJ4S-1213-R03 | 5000 L | Glass-lined | No gap — same equipment. |
| Filter & Drying | TJ4S-1212-FD03 | DN1000 | Hastelloy | TJ4S-1212-FD03 | DN1000 | Hastelloy | No gap — same equipment. |
| Store n-Heptane | TJ4S-1213- Tr06 | 500 L | Stainless steel | TJ4S-1213- Tr06 | 500 L | Stainless steel | No gap — same equipment. |

Conclusion: Although the ESA report has not yet been finalized, given that the equipment used for Full scale non saleable batches and PPQ batches is identical, and its parameters meet process requirements, the residual risk associated with any outstanding ESA activities is low. Reference the Equipment Suitability Assessment report (RA-140021030201.01<Equipment Suitability Assessment for ASYM-140852 (step 2)>).

3.3.3The Process Changes for LSN4182928/ASYM-140021 (Step 3)

The process equipment proposed for the PPQ campaign is listed below and compared with the Full Scale non-saleable batch equipment. The Step 3 Equipment Suitability Analysis (ESA) and report are in preparation and will  be completed by Asymchem prior to the step 3 PPQ campaign.

Table 5: The Step 3 Process Equipment Gap Comparison

| Intended Purpose | Full Scale non-saleable batch Equipment Code | Capacity | MOC | PPQ Equipment Code | Capacity | MOC | Comments / GAP Assessment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Reduction reaction Reactor Prepare HCl solution and NaCl solution | TJ4S-1213-R12 | 5000 L | Glass-lined | TJ4S-1213-R12 | 5000 L | Glass-lined | No gap — same equipment. |
| Cyclization reaction Reactor | TJ4S-1213-R14 | 8000 L | Glass-lined | TJ4S-1213-R14 | 8000 L | Glass-lined | No gap — same equipment. |
| Concentration&Crystallization reactor | TJ4S-1213-R06 | 3000 L | Stainless steel | TJ4S-1213-R06 | 3000 L | Stainless steel | No gap — same equipment. |
| Agitated Filter Dryer | TJ4S-1212-FD01 | DN1000 | Stainless steel | TJ4S-1212-FD01 | DN1000 | Stainless steel | No gap — same equipment. |
| Agitated Filter Dryer | TJ4S-1212-FD02 | DN1000 | Stainless steel | TJ4S-1212-FD02 | DN1000 | Stainless steel | No gap — same equipment. |
| Store n-Heptane | TJ4S-1213- Tr06 | 500 L | Stainless steel | TJ4S-1213- Tr07 | 500 L | Stainless steel | Full scale Batch Step 3 shared n-heptane storage tank TJ4S-1213-Tr06 (for controlled-rate feeding) with Step 2. A new dedicated storage tank TJ4S-1213-Tr07 is added exclusively for Step 3 to improve production efficiency. |
| Agitation Tank Prepare 2-MeTHF / n-Heptane solution | TJ4S-1212-AT01 | 500 L | Stainless steel | TJ4S-1212-AT01 | 500 L | Stainless steel | No gap — same equipment. |

Conclusion: One optimization item is identified: at full scale, Step 3 originally shared n-heptane storage tank TJ4S-1213-Tr06 (for controlled-rate feeding) with Step 2, while a new dedicated storage tank TJ4S-1213-Tr07 is added exclusively for Step 3 in the PPQ campaign to improve production scheduling efficiency. The equipment material of construction and size of TJ4S-1213-Tr06 and TJ4S-1213-Tr07 are the same. This change is an equipment optimization for operational efficiency, with no impact on process performance or product CQAs. The other equipment used for Full scale non saleable batches and PPQ batches is identical, so the residual risk associated with any outstanding ESA activities is assessed as low risk. Reference the Equipment Suitability Assessment report (RA-140021030301.01< Equipment Suitability Assessment for ASYM-140021 (step 3)>).

3.4 Specifications and Analytical Methods

3.4.1 Raw Material Specifications

The comparison of specifications and testing methods for raw materials used in the process between the Full Scale non-saleable batch and the PPQ campaign is shown below.

Table 6: The Raw Material Specification Assessment

| Material Name | Full Scale non-saleable Batch Material No. | PPQ Material No. | Full Scale non-saleable batch Spec Document | PPQ Spec Document | Full Scale non-saleable batch QSV | PPQ QSV | Gaps and Justification |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2-CTC Resin | YL003422 | YL003422 | RMS-TJ414002102.07 | RMS-TJ414002103 | QAA03550 | QAA03550 | The specification test items and analytical methods are consistent; only the quality specification version differs. |
| Fmoc-Gly-OH | YL004846 | YL004846 | RMS-TJ414002102.07 | SP-138200-02(current version) | QAA03550 | QAA03550 | Change the Acceptance criteria of Appearance from “White to off-white solid” to “White to off-white powder”: As a general term, 'solid' encompasses various forms of materials. To describe the appearance more accurately and consistently, the acceptance criteria for appearance have been updated, enabling stricter control over product quality. |
| Fmoc-L-Thr(tBu)-OH | YL003563 | YL003563 | RMS-TJ414002102.07 | SP-138389-02(current version) | QAA03550 | QAA03550 | Change the Acceptance criteria of Appearance from “White to off-white solid” to “White to off-white powder”: As a general term, 'solid' encompasses various forms of materials. To describe the appearance more accurately and consistently, the acceptance criteria for appearance have been updated, enabling stricter control over product quality. |
| Fmoc-L-Ala-OH*H2O | YL006160 | YL006160 | RMS-TJ414002102.07 | SP-138204-02(current version) | QAA03550 | QAA03550 | Change the Acceptance criteria of Appearance from “White to off-white solid” to “White to off-white powder”: As a general term, 'solid' encompasses various forms of materials. To describe the appearance more accurately and consistently, the acceptance criteria for appearance have been updated, enabling stricter control over product quality. |
| Fmoc-L-Cys(Trt)-OH | YL003565 | YL003565 | RMS-TJ414002102.07 | SP-138397-03(current version)/ | QAA03550 | QAA03550 | Change the Acceptance criteria of Appearance from “White to off-white solid” to “White to off-white powder”: As a general term, 'solid' encompasses various forms of materials. To describe the appearance more accurately and consistently, the acceptance criteria for appearance have been updated, enabling stricter control over product quality. |
| Fmoc-L-Asn(Trt)-OH | YL004843 | YL004843 | RMS-TJ414002102.07 | SP-138519-02(current version) | QAA03550 | QAA03550 | Change the Acceptance criteria of Appearance from “White to off-white solid” to “White to off-white powder”: As a general term, 'solid' encompasses various forms of materials. To describe the appearance more accurately and consistently, the acceptance criteria for appearance have been updated, enabling stricter control over product quality. |
| Boc-L-Glu-OtBu | YL008618 | YL008618 | RMS-TJ414002102.07 | SP-140413-02(current version) | QAA03550 | QAA03550 | 1. Change the Acceptance criteria of Appearance from “White to off-white solid” to “White to off-white powder”: As a general term, 'solid' encompasses various forms of materials. To describe the appearance more accurately and consistently, the acceptance criteria for appearance have been updated, enabling stricter control over product quality.) 2. Tighten the purity limit from “98.0%” to “99.0%”: according to the historical batches data, the purity is 100.0% (lot# CPr140413-02-03-01 and lot# CPr140413-02-03-02), the current production process can effectively control the level of impurities. So, the purity limit will be tightened, it can improve the quality of the product. |
| Oxyma Pure | YL005180 | YL005180 | RMS-TJ414002102.07 | RMS-TJ414002103.01 | QAA03550 | QAA03550 | No Gap. |
| PyBOP | YL002855 | YL002855 | RMS-TJ414002102.07 | RMS-TJ414002103.01 | QAA03550 | QAA03550 | No Gap. |
| DIC | YL003564 | YL003564 | RMS-TJ414002102.07 | RMS-TJ414002103.01 | QAA03550 | QAA03550 | No Gap. |
| Elemental iodine | YL003092 | YL003092 | RMS-TJ414002102.07 | RMS-TJ414002103.01 | QAA03550 | QAA03550 | No Gap. |
| N,N-Dimethylformamide | YL000336 | YL000336 | RMS-TJ414002102.07 | RMS-TJ414002103.01 | QAA03550 | QAA03550 | No Gap. |
| Ethyldiisopropylamine | YL000555 | YL000555 | RMS-TJ414002102.07 | RMS-TJ414002103.01 | QAA03550 | QAA03550 | No Gap. |
| tert-Butyl methyl ether | YL000557 | YL000557 | RMS-TJ414002102.07 | RMS-TJ414002103.01 | QAA03550 | QAA03550 | No Gap. |
| Isopropyl acetate | YL000932 | YL000932 | RMS-TJ414002102.07 | RMS-TJ414002103.01 | QAA03550 | QAA03550 | No Gap. |
| Piperidine | YL001394 | YL001394 | RMS-TJ414002102.07 | RMS-TJ414002103.01 | QAA03550 | QAA03550 | No Gap. |
| Methanol | YL000031 | YL000031 | RMS-TJ414002102.07 | RMS-TJ414002103.01 | QAA03550 | QAA03550 | No Gap. |
| Trifluoroacetic acid | YL000419 | YL000419 | RMS-TJ414002102.07 | RMS-TJ414002103.01 | QAA03550 | QAA03550 | No Gap. |
| Pyridine | YL000617 | YL000617 | RMS-TJ414002102.07 | RMS-TJ414002103.01 | QAA03550 | QAA03550 | No Gap. |
| L-Ascorbic acid | YL001990 | YL001990 | RMS-TJ414002102.07 | RMS-TJ414002103.01 | QAA03550 | QAA03550 | No Gap. |
| n-Heptane | YL000474 | YL000474 | RMS-TJ414002102.07 | RMS-TJ414002103.01 | QAA03550 | QAA03550 | No Gap. |
| Dichloromethane | YL000002 | YL000002 | RMS-TJ414002102.07 | RMS-TJ414002103.01 | QAA03550 | QAA03550 | No Gap. |
| Ethyl acetate | YL000025 | YL000025 | RMS-TJ414002102.07 | RMS-TJ414002103.01 | QAA03550 | QAA03550 | No Gap. |
| Tris(2-carboxyethyl)phosphine hydrochloride | YL008268 | YL008268 | RMS-TJ414002102.07 | RMS-TJ414002103.01 | QAA03550 | QAA03550 | No Gap. |
| 36% Hydrochloric acid | YL000451 | YL000451 | RMS-TJ414002102.07 | RMS-TJ414002103.01 | QAA03550 | QAA03550 | No Gap. |
| Sodium chloride | YL000493 | YL000493 | RMS-TJ414002102.07 | RMS-TJ414002103.01 | QAA03550 | QAA03550 | No Gap. |
| Preparative Acetonitrile | YL004696 | YL004696 | RMS-TJ414002102.07 | RMS-TJ414002103.01 | QAA03550 | QAA03550 | No Gap. |
| 2-Methyltetrahydrofuran | YL001029 | YL001029 | RMS-TJ414002102.07 | RMS-TJ414002103.01 | QAA03550 | QAA03550 | No Gap. |
| N-(((5R,8S,11S,14S,17S,20R)-20-((S)-5-(tert-butoxy)-4-((tert-butoxycarbonyl)amino)-5-oxopentanamido)-8,14-bis((R)-1-(tert-butoxy)eth yl)-11-methyl-7,10,13,16,19-pentaoxo-17-(2-oxo-2-(tritylamino)ethyl)-1,3-dithia-6,9,12,15,18-pentaazacyclohenicosane-5-cabonyl)-L-alanyl)-O-(tert-butyl)-L-threonylglycine | CP004646 | ZJ008531 | SP-140021-03 (current version) | SP-140021-04(current version) | QAA03550 | QAA03550 | Differentiated control shall be implemented for seeding material and corresponding bulk materials, with dedicated independent material codes assigned for seeding crystal to achieve distinction. For detailed control requirements, refer to seeding material control procedure for LSN4182928/ASYM-140021 (Doc. No. Memo-140021030302.01). |

Conclusion: All amino acid specifications have been converted into independent specification documents according to the change Change-TJ420260080.01. This update only adjusts the testing items, acceptable criteria, and test methods for amino acids to index independent specification documents. This change also includes updates to the seeding material; differentiated controls have been implemented for seeding material and corresponding bulk materials, with dedicated independent material codes assigned for seeding crystal to achieve distinction. Therefore, this change has no impact on product quality. Above all, this GAP do not affect the product quality.

3.4.2 In-Process Control (IPC) Items and Methods

a). The In-Process Control (IPC) Items for step 1 SPPS in LSN4182928 / ASYM-140021

The comparison of IPC items and analytical methods between the Full Scale non-saleable batch and PPQ campaign is shown below.

Table 7: The Step 1 SPPS IPC Items Gap Assessment

| Process Step | Test Item | Full Scale non-saleable Batch Criteria | PPQ Campaign Criteria | Method Reference |
| --- | --- | --- | --- | --- |
| Pre-treatment | KF | NMT 500 ppm | NMT 500 ppm | Method: from AM-140021-006 to AM-YL000336-004 |
| Amino acid coupling Completion(AA2~AA10) | Ninhydrin test | Negative | Negative | Establish a dedicated bromophenol blue method method for PPQ batch: AM-140021-043 |
| ASYM-140850 in post oxidation washing | ASYM-140850 | ≤0.5% | ≤0.5% | No Gap. AM-140021-011 |
| LOD under drying | LOD under drying | ≤ 10.0% | ≤ 9..0% | AM-140021-007 |
| ASYM-140851 after collecting | Appearance test | Light yellow to yellow solid | Light yellow to yellow solid | No Gap. AM-140021-039 |

Conclusion:

1. Pre-treatment KF test

Method AM-140021-006 has not been validated, while Method AM-YL000336-004 has been validated in the TJ4-QC Lab and the all results meet the acceptance cirteria. Update the method to AM-YL000336-004 , the determination results will be more accurate.

2.  Bromophenol blue method for amino acid coupling completion (AA2~AA10)

The  method AM-140021-043 describes the determination process, specifies the solution preparation and acceptance cirteria, and has been validated. Using the method AM-140021-043 will make the determination more standardized and the results more accurate.

3. LOD acceptance criterion： Based on the PAR study, the drying endpoint LOD acceptance criterion is tightened from 10.0% to 9.0%. The PAR study demonstrated that the drying process is capable of consistently achieving LOD below 9.0% under the established drying conditions, and the full-scale non-saleable batch data confirmed this capability. The tighter criterion provides an additional margin for residual solvent and moisture control, which supports product stability and downstream process consistency

4. Other IPC items: No gaps

b). The In-Process Control (IPC) Items for step 2 soft cleavage in LSN4182928 / ASYM-140021

The comparison of IPC items and analytical methods between the Full Scale non-saleable batch and PPQ campaign is shown below.

Table 8: The Step 2 Soft Cleavage IPC Items Gap Assessment

| Process Step | Test Item | Full Scale non-saleable Batch Criteria | PPQ Campaign Criteria | Method Reference |
| --- | --- | --- | --- | --- |
| DCM residue—after twice distillation with EA | DCM residue | ≤3% w/w | ≤3% w/w | Method: From AM-140021-015 to A M-140021-051 |
| Solvent residue under drying | EA residue, n-heptane residue, DCM residue | EA residue ≤1% w/w | EA residue ≤1% w/w | Method: From AM-140021-015 to AM-140021-051 |
|  |  | n-Heptane residue ≤2% w/w | n-Heptane residue ≤2% w/w |  |
|  |  | DCM residue≤1% w/w | DCM residue≤1% w/w |  |

Conclusion: A gap is identified in the residual solvent testing method for IPC dried solid samples of Step 2 cleavage. During the full-scale non-saleable batch campaign, three consecutive System Suitability Test (SST) failures were observed for method AM-140021-015.06, with n-heptane recovery at 90% falling outside the 95%–105% acceptance criteria, and a deviation investigation has been initiated per site procedure.

For the PPQ campaign, a new residual solvent method AM-140021-051 with DMI as diluent will be implemented based on feasibility and development studies to resolve the SST failure issue. This change is a testing method optimization for improved reliability, with no impact on the in-process control strategy and product CQAs. The new method AM-140021-51 has been validated(Validation report: AM-140021-051-VR-01.01 ), and all recoveries meet the acceptance criteria of 90.0~11.0.0% so it is assessed as low risk. All other IPC items and testing methods for Step 3 remain consistent between the full-scale non-saleable batch and PPQ campaign, with no additional gaps.

c). The In-Process Control (IPC) Items for step 3 Dithiolacetal synthesis in LSN4182928 / ASYM-140021

Table 9: The Step 3 Dithiolacetal Synthesis IPC Items Gap Assessment

| Process Step | Test Item | Full Scale non-saleable Batch Criteria | PPQ Campaign Criteria | Method Reference |
| --- | --- | --- | --- | --- |
| ASYM-140852, ASYM-141266 —stage 2 reaction mixture | ASYM-140852, ASYM-141266 | ASYM-140852 ≤0.1% area | ASYM-140852 ≤0.1% area | AM-140021-016 (The ASYM-141266 test item is removed from IPC monitoring under method AM-140021-016.) |
|  |  | ASYM-141266 ≤0.5% area | N/A |  |
| ACN residue, KF —mixture after the second distilled with 2-MeTHF | ACN residue, KF | ACN residue ≤1% w/w, | ACN residue ≤1% w/w, | No Gap. AM-140021-018 |
|  |  | KF≤2.5% w/w | KF≤2.5% w/w | No Gap. AM-140021-017 |
| Diiodomethane residue —filter cake after rinsed with 2-MeTHF/ n-heptane mixture | Diiodomethane residue | ≤0.04% area | ≤0.04% area | No Gap. AM-140021-019 |
| Solvent residue, KF —under drying | 2-MeTHF residue, Acetonitrile residue, n-Heptane residue, KF | 2-MeTHF residue≤5% w/w, w/w | 2-MeTHF residue≤5% w/w, w/w | No Gap. AM-140021-018 |
|  |  | Acetonitrile residue≤1% | Acetonitrile residue≤1% |  |
|  |  | n-Heptane residue≤1% w/w | n-Heptane residue≤1% w/w |  |
|  |  | KF≤1.8% w/w | KF≤1.8% w/w | No Gap. AM-140021-017 |

Conclusion:

Gap Analysis for Step3 Stage 2 Reaction Mixture IPC Items Difference Description

For the Step3 stage 2 reaction mixture, the saleable batch monitors both ASYM-140852 (≤0.1% area) and ASYM-141266 (≤0.5% area) via IPC testing under method AM-140021-016, while the PPQ campaign only retains ASYM-140852 testing and removes ASYM-141266 from the IPC monitoring scope.

ASYM-141266 is extremely unstable and rapidly converts to ASYM-140852 at room temperature. Under routine IPC sampling and testing conditions, stable and accurate quantitative results cannot be obtained, leading to insufficient representativeness of test data.

ASYM-141266 is prepared via derivatization of ASYM-140852, using TCEP·HCl and DIPEA as derivatization reagents. The overall residual risk of such related substances in the reaction system can be effectively covered by quantitative testing of ASYM-140852.

This adjustment is an IPC strategy optimization based on the physicochemical properties of the compound and testing feasibility. It does not reduce the level of quality control and does not constitute a quality gap.

Other IPC items: No gaps

3.4.3 Analytical Methods

a). The In-Process Control (IPC) Method Validation

The completion status of method transfer/validation for step 1~3 IPC methods is shown in Table 10.

Table 10: The Summary of IPC Method Validation

| Step No | PPQ Batches Method | Validation Protocol | Validation experiment | Validation report |
| --- | --- | --- | --- | --- |
| Step1 | AM-YL000336-004 | AM-YL000336-004-VP-01.01 (Effective Date: 05/29/2026) | Completed | AM-YL000336-004-VR-01.01 (Effective Date: 09/08/2026) |
|  | Establish a dedicated method for PPQ batch: AM-140021-043 (Bromophenol blue) | AM-140021-043-VP-01.01 (Effective Date: 08/22/2026) | Completed | AM-140021-043-VR-01.01 (Effective Date: 09/29/2026) |
|  | AM-140021-011 | AM-140021-011-VP-01.01 (Effective Date: 07/15/2026) | Completed | AM-140021-011-VR-01.01 (Effective Date: 10/07/2026) |
| Step2 | AM-140021-051 | AM-140021-051-VP-01.02 (Effective Date: 08/18/2026) | Completed | AM-140021-051-VR-01.01 Completion prior to PV Step2 start) |
|  | AM-140021-051 | AM-140021-051-VP-01.02 (Effective Date: 08/18/2026) | Completed | AM-140021-051-VR-01.01 ( Completion prior to PV Step2 start) |
| Step3 | AM-140021-016 (The ASYM-141266 test item is removed from IPC monitoring under method AM-140021-016.) | AM-140021-016-VP-01.01 (Effective Date: 09/22/2026) | Completion prior to PV step3 start | Completion prior to PV step3 start |
|  | AM-140021-018 | AM-140021-018-VP-01.02 (Effective Date: 07/24/2026) | Completed | AM-140021-018-VR-01.01 Completion prior to PV step3 start |
|  | AM-140021-017 | AM-140021-017-VP-01.01 (Effective Date: 07/10/2026) | Completed | AM-140021-017-VR-01.01 Completion prior to PV step3 start |
|  | AM-140021-019 | AM-140021-019-VP-01.01 (Effective Date: 07/09/2026) | Completed | AM-140021-019-VR-01.01 Completion prior to PV step3 start |
|  | AM-140021-018 | AM-140021-018-VP-01.02 (Effective Date: 07/24/2026) | Completed | AM-140021-018-VR-01.01 Completion prior to PV step3 start |
|  |  | AM-140021-018-VP-01.02 (Effective Date: 07/24/2026) | Completed | AM-140021-018-VR-01.01 Completion prior to PV step3 start |
|  |  | AM-140021-018-VP-01.02 (Effective Date: 07/24/2026) | Completed | AM-140021-018-VR-01.01 Completion prior to PV step3 start |
|  | AM-140021-017 | AM-140021-017-VP-01.01 (Effective Date: 07/10/2026） | Completed | AM-140021-017-VR-01.01 Completion prior to PV step3 start |

Conclusion:

The validation protocol and experimental work for IPC test methods have been completed with the exception of method AM-140021-016where the validation report is in preparation. For method AM-140021-016, The method will be fully approved and its validation report will be completed prior to PV Step 3 start. Thus, there is no risk.

b). The Intermediate Specification and Release Method Validation

The comparison of Intermediate specifications between the Full Scale non-saleable batch and PPQ campaigns is shown in Table 11.

Table 11: Intermediate Release Specification Comparison and Method Validation

| Test Items |  | Current spec for full scale |  | Proposed spec for PPQ |  | Validation Protocol | Validation experiment | Validation report |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Method | Acceptance Criteria | Method | Acceptance Criteria |  |  |  |
| Description | Appearance | AM-001 | White to yellow solid | AM-140021-042 | White to yellow solid | N/A | N/A | N/A |
| Test | Identification by UHPLC | N/A | N/A | AM-140021-012 | Conforms to the reference standard | AM-140021-012-VP-01.02(Effective Date: 08/12/2026) | Completed | AM-140021-012-VR-01.01(Effective Date: TBD) |
|  | Purity | AM-140021-012 | Purity (include dimer and not include trimer） Report | AM-140021-012 | Purity：Report Purity (include dimer and trimer): Report |  |  |  |
|  |  |  | Dimer is not reported separately |  | Dimer: Report |  |  |  |
|  |  |  | Trimer is not reported separately |  | Trimer: Report |  |  |  |
|  |  |  | No total impurity control |  | Total impurities(not include dimer+ trimer) ≤10.0% |  |  |  |
|  |  |  | No unspecified impurity control |  | Any individual impurities (Report individual impurities ≥ 0.10% by RRT) ≤1.0% |  |  |  |
|  | Residual TFA | AM-140021-013 | Report | AM-140021-013 | ≤0.2% | AM-140021-013-VP-01.02(Effective Date: 06/10/2026) | Completed | AM-140021-013-VR-01.01 (Effective Date: 09/29/2026) |
|  | Residual Pyridine | AM-140021-014 | Report | AM-140021-014 | ≤0.5% | AM-140021-014-VP-01.02(Effective Date: 07/08/2026) | Completed | AM-140021-014-VR-01.01(Effective Date: TBD) |

Conclusion:

All validation protocols have been approved and are effective, and all validation experiments are complete. The remaining action items are to finalize and approve the methods and validation reports for AM-140021-012, AM-140021-013, and AM-140021-014. These documents will be approved and effective before the start of PPQ Step 2, so that all intermediate release testing uses fully validated methods. These open items do not affect product quality, and the associated risk is low.

c). The Product Specification and Release Method Validation

The comparison of Product Quality Specifications for LSN4182928 / ASYM-140021 between the Full Scale non-saleable batch and PPQ campaigns is shown in Table 12.

Table 12: The Product Quality Specifications Comparison and Method Validation

| Test Items |  | Current spec for full scale |  |  | Proposed spec for PPQ |  |  | Protocol | Validation experiment |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Method | Acceptance Criteria |  | Method | Acceptance Criteria |  |  |  |
| Description | Appearance | AM-140021-001 | White to yellow solid |  | AM-140021-001 | White to yellow solid |  | N/A | CompletedN/A |
| Identification | Identification by UHPLC | AM-140021-003 | Conforms to the reference standard |  | AM-140021-003 | Conforms to the reference standard |  | AM-140021-003-VP-01.01 (Effective Date: 09/04/2024) | Completed |
|  | Identification by MS | AM-013 | Consistent with the exact mass |  | AM-140021-044 | Consistent with the exact mass |  | AM-140021-044-VP-01 (Effective Date: 07/09/2026) | Completed |
| Test | Purity and related impurities by UHPLC | AM-140021-003 | Purity | ≥ 90.0% | AM-140021-003 | Purity | ≥ 90.0% | AM-140021-003-VP-01.01 (Effective Date: 09/04/2024) | Completed |
|  |  |  | Total impurities | ≤ 10.0% |  | Total impurities | ≤ 10.0% |  |  |
|  |  |  | Any individual impurities | ≤ 1.0% |  | Dimer | 1.5% |  |  |
|  |  |  |  |  |  | +Gly impuritiy | 0.5% |  |  |
|  |  |  | Report individual impurities ≥ 0.10% by RRT |  |  | Any individual impurities (Report individual impurities ≥ 0.10% by RRT) | ≤ 0.5% |  |  |
|  | Assay by UHPLC | AM-140021-003 | ≥ 80.0 and ≤ 110.0 (%w/w) |  | AM-140021-003 | ≥ 80.0 (%w/w) |  |  |  |
|  | Water content by KF | AM-140021-002 | ≤ 2.0%w/w |  | AM-140021-002 | Report |  | AM-140021-002-VP-01.01 (Effective Date: 08/27/2024) | Completed |
|  | Trifluoroacetic acid content by HPLC | AM-140021-004 | ≤ 0.1% |  | AM-140021-004 | Report* |  | AM-140021-004-VP-01.01 (Effective Date: 08/24/2024) | Completed |
|  | Residual CH2I2 by UHPLC | AM-140021-024 | ≤ 0.06% |  | AM-140021-024 | TBD |  | AM-140021-024-VP-01.01 (Effective Date: 09/27/2024) | Completed |
|  | Residual TCEP&TCEP-oxide by HPLC | AM-140021-025 | Report |  | AM-140021-025 | TBD |  | AM-140021-025-VP-01.01 (Effective Date: 09/27/2024) | Completed |
|  | Residual organic solvents by HS-GC | AM-140021-005 | Methanol | Report | AM-140021-005 | Methanol | Report* | AM-140021-005-VP-01.01 (Effective Date: 09/21/2024) | Completed |
|  |  |  | Acetonitrile | Report |  | Acetonitrile | TBD |  |  |
|  |  |  | Dichloromethane | ≤600ppm |  | Dichloromethane | TBD |  |  |
|  |  |  | Methyl tert-Butyl Ether | Report |  | Methyl tert-Butyl Ether | TBD |  |  |
|  |  |  | n-Heptane | Report |  | n-Heptane | TBD |  |  |
|  |  |  | Ethyl acetate | Report |  | Ethyl acetate | TBD |  |  |
|  |  |  | N,N-Dimethylformamide | ≤880ppm |  | N,N-Dimethylformamide | TBD |  |  |
|  |  | AM-140021-020 | 2-Methyltetrahydrofuran | Report | AM-140021-020 | 2-Methyltetrahydrofuran | TBD | AM-140021-020-VP-01.01 (Effective Date: 09/21/2024) | Completed |
|  |  |  | Isopropyl acetate | ≤5000ppm |  | Isopropyl acetate | TBD |  |  |
|  |  |  | N,N-Diisopropylethylamine | ≤1500ppm |  | N,N-Diisopropylethylamine | TBD |  |  |
|  |  |  | Pyridine | Report |  | Pyridine | TBD |  |  |
|  |  |  | Piperidine | Report |  | Piperidine | TBD |  |  |

*Note: Residual solvent limits remain unchanged from the current specification. These solvents are monitored through a characterization protocol and are not included as formal PPQ release limits; the results are reported  for process understanding.

Conclusion:

The majority of PPQ release analytical methods have been validated; the supplemental validation protocol are currently under review with validation experiment pending, to be completed prior to PPQ release testing. These gaps do not affect product quality.

d) Laboratory Status

Laboratory facilities and systems supporting Steps 1-3 IPC and PPQ testing have been reviewed. All critical analytical instruments are qualified (IQ/OQ/PQ completed) and within valid calibration periods. Laboratory environment (temperature, humidity, fume hoods) meets the requirements for the intended analytical procedures. Consumables including chromatography columns, sample vials, filters and solvents are available and released for use. Laboratory data acquisition systems are accessible and configured properly for data recording, electronic traceability and GMP compliance.

e) Analyst Qualification

All analysts assigned to perform Steps 1-3 IPC and PPQ testing have completed required GMP training, the training of methods and hands on practical exercises for the relevant test methods will be completed prior to usage of the methods. Analyst qualification assessments (proficiency tests) have been conducted. Only analysts with successfully passed qualification are authorized to perform the corresponding IPC and PPQ sample testing. Training records and qualification documentation are maintained on file. No unqualified personnel will conduct testing activities for PPQ campaign.

f) Reference standard qualification status

All reference standards used for Steps 1–3 IPC and PPQ testing have been qualified and are within their valid expiry periods. Sufficient inventory is available to support the entire PPQ campaign. The only exception is the dimer reference standard, which is currently under preparation. The preparation progress of this reference standard has been included in the action plan with a defined owner and target date, and does not affect PPQ initiation. No testing activities relying on this reference standard will be initiated until it is ready.

3.5 Cleaning Validation

Table 13: The Gap Analysis for Cleaning Validation

| Focus Area | Current Status | Gap Analysis | Risk |
| --- | --- | --- | --- |
| Current cleaning validation status | Step 1 CVP under revision; Step 2 and Step 3 CVP drafts pending review | CVPs not yet approved | Medium |
| Outstanding development activities | Solubility testing of target residues in candidate cleaning solvents has been completed | The cleaning frequency for Steps 2 and 3 requires further discussion. | Low |
| ARL/PDE strategy | All determined | No Gap | Low |
| Analytical method readiness | Cleaning detection method validation completed for step 1 Cleaning detection method development and validation completed based on methanol as the cleaning solvent for step 2 and step 3 | As the cleaning solvent needs to be changed to process solvent, the cleaning detection methods for Steps 2 and 3 need to be re-developed and re-validated | Medium |
| Dirty hold time | All determined | No Gap | Low |
| Clean hold time | All determined | No Gap | Low |

Cleaning validation is a critical component of the contamination control strategy and PPQ readiness. The project consists of three steps. The Step 1 CVP is under revision, and the Step 2 and Step 3 CVPs have been drafted and are pending review. All three CVPs will be approved prior to PPQ execution. Cleaning validation will be executed concurrently with PPQ, and the CVR will be completed prior to product release. The outstanding development activities mainly involve the development and validation of cleaning detection methods for Steps 2 and 3 following the change of cleaning solvent. All gaps have been incorporated into the action plan with defined owners and target dates, and no adverse impact on PPQ execution or product quality is anticipated.

3.6 Technology Transfer Gap Assessment (by Area)

The table below provides the structured gap assessment across all key technology transfer areas. Risk classification follows Table 2.

The table below provides the structured gap assessment across all key technology transfer areas. Risk classification follows Table 2.

Per Table 2, risk ranking assumes no mitigation has been implemented. A 'Low' ranking is assigned only where available data or extensive prior knowledge demonstrate no or low correlation with CQAs, independent of planned future activities; the listed activity (e.g., routine training, document update) is a procedural prerequisite under the established quality system for an unchanged process, not a control for a new hazard. Items that rely on not-yet-completed validation, qualification or assessment to control risk are ranked Medium and tracked in Section 4 until completed.

Table 14: The Technology Transfer Gap Assessment

| Area Evaluated | Sending Site (ASYM / Current Process) | Receiving Site Status — Challenges, Gaps or Differences | Risk to product Quality | Report Reference, Risk Ranking Rationale, Mitigation Plan and/or Action |
| --- | --- | --- | --- | --- |
| Due Diligence |  |  |  |  |
| Quality Due Diligence Assessment (QDDA) | Provides outcomes and conclusions of the QDDA with any gaps and CAPAs identified ASYM GQAAC pre-commercialization audit completed | Relevant personnel shall be present on-site to accompany auditors and respond to all relevant inquiries. Relevant documents and attachments shall be provided promptly upon request. Timely follow-up and confirmation shall be performed to verify resolution of all issues, preventing omissions in communication records. The QA organization shall provide the corrective action plan to the customer within 30 calendar days and timely update the customer on the progress of corrective actions. | Low | Risk ranking rationale: QDDA completed; the CAPAs are administrative and have no process/CQA impact; per Table 2 there is no or low correlation with CQA. Risk ranking rationale: QA shall archive all relevant audit documents Corrective Actions and Preventive Actions Management(QA-009) |
| Facility |  |  |  |  |
| Facility Design, Capacity and Environmental Controls | Describe capacity adequacy, room classifications, process/material/waste flows, contamination control strategy (CCS) Any special temperature, humidity or light protection requirements Cross-contamination controls | The TJ4 site adopts cGMP-compliant facility design, with sufficient production space, qualified utility systems and production capacity to fully support the SPPS manufacturing activities. (SMF-TJ4-001) | Low |  | Risk ranking rationale: facility qualified and in routine use; no facility change; no CQA impact. Site Master File for Asymchem Life science (Tianjin) Co., Ltd (SMF-TJ4-001) Risk Assessment Report for Cross-contamination Control strategy in LSN4182928/ASYM-140021 production (RA-1400210301.01) |
| raw material; in-process intermediate ASYM-140851/ intermediate LSN4214882/ASYM-140852/ product LSN4182928 /ASYM-140021 Storage | Storage temperature and humidity Room classification Light protection On-site or off-site Capacity | Materials have been stored in accordance with relevant specifications to ensure they are maintained under appropriate storage conditions and safeguard product quality. The process intermediate will be stored in accordance with relevant specifications. | Low |  | Risk ranking rationale: storage follows existing qualified specifications; no change to storage conditions. Storage condition monitoring of storage area and equipment(DS) (DS-MM-008) |
| Utilities |  |  |  |  |
| Water | Grade of water used in each process step Minimum water grade required by control strategy Water specifications | The purified water system shall be disinfected and sterilized in accordance with relevant procedures to reduce the risk of microbial contamination within the water system and ensure the water quality meets process requirements. | Low |  | Risk ranking rationale: existing qualified water system; no change; no CQA impact. Risk ranking rationale: existing qualified water system; no change; no CQA impact. Disinfection procedure of water system(DS) (DS-GMP-019) Procedure for in-house made water system monitoring and service instruction(DS)(DS-GMP-020) |
| Process Gases (Nitrogen.) | Filtered and monitored process gases used Nitrogen for SPPS synthesizer, storage tank inertion, transfer lines | The nitrogen system distribution, nitrogen pipeline filtration, replacement frequency of fittings and equipment maintenance shall be implemented in accordance with relevant procedures. | Low |  | Risk ranking rationale: existing qualified nitrogen system; no change; no CQA impact. Nitrogen Distribution System Management Procedure (GMP-285) |
| Heat Transfer Fluids / Plant Steam | Heat transfer fluids used in vessel jackets Qualified temperature range Expected variability around temperature set points | A utility system management SOP is established at the site to guarantee uninterrupted smooth production in case of system malfunctions. | Low |  | Risk ranking rationale: existing qualified utility system; no change; no CQA impact. Power supplying system management procedure in TJ4 site (DS) (DS-GMP-065) |
| Personnel and Safety |  |  |  |  |
| Batch Scheduling / Manufacturing Shifts | Describe shift schedule at sending site Confirm impact of shift schedule on hold times, contact time limits | Asymchem shift schedule (8 h/day, 6 days/week * 4 four-shift operation Pre-shift briefings are held before taking up posts, and shift handover discipline shall be implemented via on-site handover. | low |  | Risk ranking rationale: shift schedule unchanged; hold/contact times unchanged; no CQA impact. Requirements for PAR and NOR parameters are specified in batch records. Pre-production training will be conducted prior to manufacturing. |
| Training, Capability and Experience | How is MOR training performed and by whom? Do operators sign a log confirming participation? Experience level of operators with this process type? | Personnel training shall be completed prior to project initiation in accordance with process validation requirements. QA shall conduct training on key procedures prior to the start of validation production. All operators shall sign the training log to confirm their participation. | Low |  | Risk ranking rationale: routine GMP training under the established program; process unchanged; training is a procedural prerequisite, not a control for a new hazard. Executive procedure of production projects(DS) (DS-GMP-030) Employee training (ASM-003) |
| Safety / MSDS / Process Safety Information (PSI) | SDS / MSDS available for all materials? Process Safety Information (PSI) / GIPSM available? PHIS and PHA completed? Special equipment or set-up for safety purposes? | SDS documents is available for raw materials. PHA shall be completed prior to the execution of PPQ batches. And PHIS will be complete before commercial production | Medium |  | Procedure for Chemical Classification, Labelling and SDS Management(EHS-085-P01.V02) Process Hazard Analysis (PHA) Management Procedure (EHS-G-8.1-P02-M02.V01) |
| Cleaning and Sanitising |  |  |  |  |
| Cleaning and Sanitising Agents | Sanitising/cleaning agents used for equipment Product compatibility data with cleaning agents Cleaning validation carryover limits established | Appropriate cleaning agents has been determined based on material properties in accordance with relevant SOPs; suitable carryover limits for cleaning validation have been established according to equipment usage | Low |  | Risk ranking rationale: cleaning agents and carryover limits established; no change; no CQA impact. Facility disinfection procedure (DS) (DS-GMP-006) Equipment cleaning management procedure for GMP production(DS) (DS-GMP-003) |
| Cleaning Validation | Cleaning validation status for equipment dedicated to this product Carryover limits established based on product toxicology / PDE Analytical method for cleaning validation swab / rinse testing | Asymchem shall develop appropriate cleaning methods for cleaning equipment used in LSN4182928 /ASYM-140021 manufacturing during PPQ Cleaning testing activities shall be carried out in accordance with relevant cleaning procedures in Asymchem | Medium |  | Equipment cleaning management procedure for GMP production(DS) (DS-GMP-003) Cleaning validation(DS) (DS-GMP-043) |
| Raw Materials and Registered Starting Materials |  |  |  |  |
| RSM / Critical Material Receipt and Storage | RSM receipt testing strategy (on receipt or just before use?) Sampling strategy (opening containers on receipt, or using supplier samples?) Temperature excursion assessment required? Sufficient storage capacity and alarm strategy? Light protection, humidity control, freeze/thaw areas? | The Asymchem establish standard operating procedures for the receipt, inspection, sampling, testing, disposal and distribution of production materials to ensure that raw materials remain under controlled supervision with complete and proper records. | Low |  | Risk ranking rationale: existing receipt SOP; no change to receipt strategy; no CQA impact. Receipt, Release and Distribution of Raw Material for Production(DS) (DS-MM-004) |
| RSM / Raw Material Vendor Qualification | Are all approved suppliers qualified per supplier qualification SOP? Vendor qualification strategy for any new suppliers CoA limits vs receipt limits — are supplier CoAs wider than Lilly receipt limits? | All suppliers have completed qualification assessment and are listed on the Approved Supplier List | Low |  | Risk ranking rationale: all suppliers qualified and on the approved list; no change; no CQA impact. Supplier Control (MM-046) |
| RSM / Critical Material Shipping | Air vs. sea shipment logistics Temperature-controlled shipping requirements Shipping qualification status Receipt testing strategy | Corresponding SOPs shall be followed in accordance with the different stages of materials | Low |  | Risk ranking rationale: existing shipping SOP; no change; no CQA impact. Transferring between sites(MM-020) Receipt, Release and Distribution of Raw Material for Production(DS) (DS-MM-004) |
| Raw Material Dispensing | Appropriate dispensing equipment available (scales, tolerances, significant digits)? Nitrogen protection or humidity control required during dispensing? Special dispensing environment required? | Asymchem has formulated relevant procedures to support the material dispensing environment, covering room clearance, dispensing room usage and daily management, inspection, calibration and operation of weighing instruments, and inert gas protection for process equipment. | Low |  | Risk ranking rationale: existing dispensing SOP and qualified equipment; no change; no CQA impact. Changeover in production area/room(DS) (DS-GMP-007) Sampling / Dispensing Room Management(DS) (DS-MM-016) Inert gas protection for processing equipment(GMP-272) |
| Process and Equipment |  |  |  |  |
| Equipment Qualification (IQ/OQ/PQ) | All manufacturing equipment qualified to current standards Maintenance/PM/calibration systems in place Equipment capabilities and measurement tolerances defined Sufficient qualified equipment available to meet production demand | Step 1 Equipment Suitability Analysis (ESA) Preliminary assessment has been completed, and the equipment meets the requirements of the production process. Step 2 and step 3 Equipment Suitability Analysis (ESA) are in progress and will be completed prior to PPQ production for each step. Equipment qualification status IQ/OQ/PQ Has completed | Medium |  | Equipment suitability assessment(RA-140021030101.01/RA-140021030201.01/RA-140021030301.01) Facility/Equipment/Utility preventative maintenance management(DS) (DS-GMP-022) Validation and qualification of facility, utility and equipment(GMP-026) |
| Batch Size / Scale | Confirm no batch size increase between sending and receiving site If batch size change: use Lilly SURI tool for scale-up risk identification Assess impact on sampling plan and processing time limits | The molar charging quantity of PPQ batches remains unchanged. | Low |  | Risk ranking rationale: no batch size change; no scale-up risk; no CQA impact. No change. |
| Vessel Agitation (Mixing / Agitation) | Vessel design adequate for raw material dissolution and processing Power/Volume (P/V) ratio experience Method of addition to vessel Safety implications of mixing/agitation | The agitator used for prepared DIC/DMF solution has been changed from impeller type to propeller type. The agitator for prepared Iodine/DMF solution has been changed from double-layer four-bladed inclined paddle type to general impeller type. The relevant equipment suitability assessment has been completed. | Low |  | Risk ranking rationale: agitator change assessed in the completed ESA; homogeneous mixtures, minimal impact; no CQA impact. Both the DIC/DMF solution and Iodine /DMF solution form homogeneous mixtures after dissolution, and their uniformity is minimally affected by agitation types. |
| Vessel Sampling and Transfer | In-process sampling locations appropriate per APIEM-LD-243? Mode of product transfer (gravity / nitrogen / pump) Pressure / temperature monitoring and data historian links OOS audible alarms? | Sampling and sample handling procedures are specified within MOR and TSP documents. Sampling and testing operations shall be carried out in accordance with the relevant company sampling and testing procedures. The company has formulated relevant procedures to ensure the transfer, storage and testing of test samples are under control. Both the prepared DIC/DMF solution and Iodine/DMF solution are transferred via fixed pipelines with pumps. Temperature, humidity and differential pressure monitoring systems shall be managed and used per relevant company SOPs to ensure stable and effective operation of the systems. | Low |  | Risk ranking rationale: existing sampling SOP and fixed pipelines; no change; no CQA impact. Sampling and testing for raw material and product(DS) (DS-AC-004) Analytical sample management(AC-019) Fixed pipelines reduce the risk of cross-contamination. Temperature, Humidity and Pressure Difference Monitoring System Management Procedure (GMP-331) |
| In-Process Filtration (non-API) | Filter locations, MOC, porosity Filter change frequency (per batch / PM) Emergency change-out process defined? | Filter replacement and maintenance shall be performed in accordance with relevant company procedures. Asymchem has established procedures for the change management of all production-related hardware and software. | Low |  | Risk ranking rationale: existing filtration SOP; no change; no CQA impact. Equipment and facility maintenance manual (QM03025) Processing aid materials management procedure （DS-MM-015） |
| API Process Filtration / Final Filtration | Is this product an injectable API requiring sterile filtration? Is filtration part of API bioburden control strategy? Filter integrity testing method and limits defined In-use times and filter sizes appropriate for batch size | The replacement of fluid filters shall be implemented in accordance with the relevant procedures for equipment component management. | Low |  | Risk ranking rationale: existing filtration SOP; no change; no CQA impact. Equipment fitting management procedure(DS-GMP-026) |
| API Processing / Hold Times | Data supporting multiple temperature cycles (freeze/thaw)? Processing time limits established Transport time from processing area to storage within validated limits Shipment qualification for all configurations used? Material dating aligned with manufacturing/shipping schedules? | Operational time requirements will be clearly specified in the MOR. Utility Systems / Equipment Damage / Impact of Deviations / Test Data / Analytical Data / Material Release / Other Force Majeure Factors Asymchem has established guidelines for deviation reporting and investigation to identify root causes of deviations, implement corrective and preventive actions, and drive continuous improvement of the quality system. | Low |  | Risk ranking rationale: hold times defined in the existing MOR; no change; no CQA impact. MOR-TJ414002101 MOR-TJ414002102 MOR-TJ414002103 |
| Packaging / Final Sampling | Room classification for packaging area Open vs. closed (BIBO) packaging operations In-process controls, sampling method and volumes Glove box use — pressure and integrity evaluation Cleaning method for packaging area Is product milled or sieved? | Asymchem has established procedures for packaging and labelling of chemical products. Asymchem has established procedures for sampling and testing. Packaging material and Completed drug product Asymchem has established relevant procedures for shared facility control management and contamination control strategy. | Low |  | Risk ranking rationale: existing packaging SOP; no change; no CQA impact. Completed Product Packaging and Labeling(DS) (DS-MM-010) Contamination control strategy (QAP-022) Control procedure of shared facility in API production. (DS-GMP-011) |
| QC & Contract Laboratories |  |  |  |  |
| Facility and Instrumentation | Appropriate laboratory equipment available for all DS, DP and raw material methods New instruments/methods required? | A dedicated analytical department and team are available with adequate lab facilities and equipment to cover all test methods of DS, Laboratory equipment are available for the ASYM-140021 commercial production and raw material methods | Low |  | Risk ranking rationale: all instruments qualified and calibrated; no change; no CQA impact. Site Master File for Asymchem Life science (Tianjin) Co., Ltd (SMF-TJ4-001) Buildings, facilities and equipment are subject to qualification and validation as required (GMP-026) |
| Analytical Methods | Methods transferred, validated/verified for DS, RSMs and raw materials Sample holding times validated? Product matrix/solvent compatibility with sample containers confirmed? Calibration ranges current? New methods required for cleaning validation? | Asymchem has relevant guidelines for the establishment, verification, validation and transfer of analytical methods, Validation is performed for final product, intermediate, IPC and RSM methods, and raw material methods are verified as appropriate against the approved independent specification documents. Raw material Asymchem has established a standard procedure for the management of chemical intermediates to govern the sampling, testing, storage, release and distribution of chemical intermediates. Asymchem has SOPs and guiding documents related to sampling containers. | Low |  | Risk ranking rationale: methods established/validated under the existing system and raw material methods verified; no change to core methods; no CQA impact. Analytical Method Establishment, Verification, Validation and Transfer (AC-002) Chemical intermediate management(DS) (DS-MM-003) Sampling and testing for raw material and product(DS) (DS-AC-004) Guideline for Sampling of Packaging Material (QM04024) |
| Reference Standards | Reference standards available for all methods New storage conditions required? Reference standard qualification completed? | Asymchem has established a standard procedure governing the sourcing, testing, storage, usage, re-testing and disposal of reference standards. And qualification of reference standards has been completed. | Low |  | Risk ranking rationale: reference standards qualified and within expiry; no change; no CQA impact. Standard Material Management (AC-020) Chemical Macromolecular Standard Material Management(DS) (DS-AC-016) |
| Stability Programme | Stability programme includes all required ICH conditions Stability chambers available and qualified Sufficient chamber capacity Stability data required to support tech transfer identified | Asymchem has established a management procedure for stability chambers to ensure compliance with all stability study requirements. Stability chambers are available and qualified Chamber capacity are sufficient Asymchem has established a management procedure for Stability study procedure | Low |  | Risk ranking rationale: stability program and chambers qualified; no change; no CQA impact. Stability chamber management procedure (AC-163) Stability testing management procedure(DS) (DS-AC-003) |
| Laboratory Personnel | Personnel trained and qualified for all analytical methods Lab shift structure compatible with in-process testing requirements | Training and qualification evaluation documents are available to guarantee analysts can run complex analytical instruments, maintain proper data management standards and prove their expertise in relevant fields. And all analytical methods will be trained and qualified before PPQ batches Asymchem has established an employee training management system to ensure all staff meet occupational competency requirements. Asymchem shift schedule (12 h / day, 4 days / week * four-shift operation | Low |  | Risk ranking rationale: routine analyst qualification under the established program; methods unchanged; qualification is a prerequisite, not a control for a new hazard. Training Manual for Physical and Chemical Analysis Laboratory(QM04019) Employee training (ASM-003) |
| Sample Preparation and Handling | Analytical methods contain detailed sample preparation and handling instructions Any matrices known to be difficult or prone to variability? | Sampling and testing operations shall be carried out in accordance with the relevant company sampling and testing procedures. And the analytical methods include detailed instructions for sample preparation, sample handling as well as the testing procedures. | Low |  | Risk ranking rationale: methods contain detailed sample handling instructions; no change; no CQA impact. TSP-1400210310.01 TSP-1400210311.01 TSP-1400210312.01 |
| Technical Studies |  |  |  |  |
| Elemental Impurities Assessment | Elemental impurities risk assessment completed per ICH Q3D? Local data generated for new equipment / site? Risk of elemental impurity presence in product evaluated? | Asymchem has clearly defined internal requirements for the application scope and limits of elemental impurities according to ICH Q3D | Low |  | Risk ranking rationale: ICH Q3D assessment; no new equipment introducing elemental risk; no or low CQA correlation. Guideline For Elemental Impurities (QM04187) |
| Nitrosamine Risk Assessment | Nitrosamine risk assessment completed per applicable regulatory guidance Nitrosamine levels adequate to ensure patient safety Risk of nitrosamine formation in product evaluated | Asymchem is conducting the nitrosamine risk assessment per applicable regulatory guidelines. | Low |  | Risk ranking rationale: nitrosamine control strategy established; no new risk; no or low CQA correlation. N-Nitrosamine impurity control strategy (QAP-021) |
| Residual Solvent Assessment | Residual solvent risk assessment completed per ICH Q3C (R8) Solvents used in process evaluated for Class 1, 2, 3 classification Method available to test residual solvents in DS? | Asymchem conducts residual solvent risk assessment in accordance with the ICH Q3C guideline. Residual solvent in DS test methods are fully established and validated. | Low |  | Risk ranking rationale: ICH Q3C assessment; residual solvent methods validated; no change; no CQA impact. Analytical Method Establishment, Verification, Validation and Transfer (AC-002) |

# 4. Summary Risk Mitigation / Action Plan

The table below summarizes all gaps, differences and associated actions identified in Section 3. Owner functions and milestone dates must be confirmed by the Technology Transfer Team at project initiation. This table should be reviewed at each project Manufacturability Review.

Table 11: The Summary of Gap Assessment, Risk Mitigation and Action Plan

| Area Evaluated | Gap / Difference | Risk to product CQAs | Action Plan | Owner (Function) | Milestone* |
| --- | --- | --- | --- | --- | --- |
| Due Diligence |  |  |  |  |  |  |  |  |
| N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |
| Facility |  |  |  |  |  |  |  |  |
| N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |
| Utilities |  |  |  |  |  |  |  |  |
| N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |
| Personnel / Safety |  |  |  |  |  |  |  |  |
| PHA | No Gap PHA Checklist -CPo140021-03-01 has been completed. | Low |  |  |  | No Action | EHS | Completed |
| PHIS | No Gap Process Hazard Identification Summary Report for CPo140021-03 has been completed. | Low |  |  |  | No Action | EHS | Completed |
| Process and Equipment |  |  |  |  |  |  |  |  |
| Process | The post-cleavage rinse volume is increased from 5 volumes to 8 volumes | Low | Relevant contents have been filled in Change-CPo140021-030202.01 | CMMD | Assigned Owner: Yu Zhang Due Date: 11/05/2026 Item status and Closure criteria: Change control sign-off |
| Process | Revised per Manufacturing Operation Record | Low | This update was implemented upon joint discussion and confirmation among Production, Customer, QAN/A | CMMD | Assigned Owner: Yu Zhang Due Date: 10/22/2026 Item status and Closure criteria: Change control sign-off |
| Process | The process understanding, historical manufacturing experience, CPP rationale and control strategy knowledge have not been transferred and implemented | Medium | Documented training will be provided to the involved personnel prior to PPQ production initiation. | CMMD | Assigned Owner: Yu Zhang Due Date: 10/22/2026 Item status and Closure criteria: Complete the training. |
| Process | MOR is in preparation. | Low | The MOR to-do list: MOR-TJ414002101 MOR-TJ414002102 MOR-TJ414002103 | CMMD | Assigned Owner: Yu Zhang Step1：Due Date: 10/20//2026 Step2：Due Date: 11/05//2026 Step3：Due Date: 11/20//2026 |
| Equipment | Step3:Add the new tank to storage n-heptane | Low | Use dedicated n-heptane tank TJ4S-1213-Tr07 for Step3 PPQ; complete equipment suitability assessment (RA-140021030301.01). | CMMD | Assigned Owner: Yu Zhang Due Date: 11/20//2026 Item status and Closure criteria: ESA sign-off |
| Equipment | Replace the new thermowell in step 2 cleavage tank | Low | Replace the thermowell of reactor TJ4S-1212-R07; perform equipment re-validation and engineering re-assessment after replacement. | Production | Assigned Owner: Hui Ma Due Date: 10/22/2026 Item status and Closure criteria: complete equipment re-validation and engineering re-assessment |
| Equipment | For equipment automation upgrade | Low | Complete DCS integration; finish supplementary qualification of field instruments; perform required equipment re-validation / engineering assessment for modified/added equipment. | Production | Assigned Owner: Hui Ma Due Date: 10/22/2026 Item status and Closure criteria: complete equipment re-validation and engineering re-assessment |
| ESA | The step 2 Equipment suitability assessment(RA-140021030201.01) is not yet finalized. | Medium | Finalize and sign off the Equipment suitability assessment report(RA-140021030201.01) | CMMD | Assigned Owner: Yu Zhang Due Date: 11/05/2026 Item status and Closure criteria: ESA sign-off |
|  | The step 3 Equipment suitability assessment(RA-140021030301.01) is not yet finalized. | Medium | Finalize and sign off the Equipment suitability assessment report (RA-140021030301.01) | CMMD | Assigned Owner: Yu Zhang Due Date: 11/20/2026 Item status and Closure criteria: ESA sign-off |
| Cleaning Validation |  |  |  |  |  |
| Cleaning Validation | Cleaning validation gaps identified for product-dedicated equipment: cleaning validation status, carryover limits based on toxicology/PDE, and analytical method for swab/rinse testing. | Medium | Develop appropriate cleaning methods during PPQ; establish toxicology/PDE-based carryover limits; perform cleaning testing per DS-GMP-003 and DS-GMP-043. | CMMD | Assigned Owner: Yu Zhang Due Date: 11/20/2026 Item status and Closure criteria: CVP sign-off |
| Analytical method readiness | As the cleaning solvent needs to be changed to process solvent, the cleaning detection methods for Steps 2 and 3 need to be re-developed and re-validated | Medium | Method development and validation will be initiated as soon as possible. | QC | Assigned Owner: Haini Wang Due Date: 11/20/2026 Item status and Closure criteria: complete the cleaning detect method validation |
| Materials |  |  |  |  |  |  |  |  |
| Raw material supplier | A new raw material supplier has been added. | Low | Relevant contents have been filled in Change-140021-030103.01 | CMMD | The change control is signed-off |
| Seed material specification | Differentiated control shall be implemented for seeding material and corresponding bulk materials, with dedicated independent material codes assigned for seeding crystal to achieve distinction. For detailed control requirements, refer to seeding material control procedure for LSN4182928/ASYM-140021 | Low | Relevant contents have been filled in Change-140021-030304.01 | ARD | Assigned Owner: Yongle Liu Due Date: 11/20/2026 Item status and Closure criteria: complete equipment re-validation and engineering re-assessment |
| QC & Contract Labs |  |  |  |  |  |
| Analytical Methods – Step 2 Residual Solvent | A gap was identified for residual solvent testing method for IPC dried solid samples of Step 2 cleavage. During full-scale non-saleable batch campaign, three consecutive SST failures were observed for method AM-140021-015.06, n-heptane recovery (90%) out of 95–105% acceptance criteria. Deviation investigation initiated per site procedure. | Low | Implement new residual solvent method AM-140021-051 (using DMI as diluent) for PPQ campaign based on feasibility & development studies to resolve SST failure. | ARD | Assigned Owner: Yongle Liu Due Date: 11/05/2026 Item status and Closure criteria: complete the new method validation report |
| Analytical Methods – Step 3 Reaction Monitoring IPC | Step3 stage2 reaction mixture: saleable batches monitor both ASYM-140852 and ASYM-141266 by IPC method AM-140021-016; PPQ removes ASYM-141266 from IPC scope. ASYM-141266 is unstable at room temperature and quickly converts to ASYM-140852, leading to unreliable quantitative IPC results. | Low | Optimize Step3 stage2 IPC strategy. Remove ASYM-141266 from routine IPC testing; retain ASYM-140852 IPC testing. | ARD | Assigned Owner: Yongle Liu Due Date: 11/20/2026 Item status and Closure criteria: complete relevant method validation report |
| IPC Methods | Clear quantitative requirements are specified for both sample handling procedures and test result acceptance criteria for IPC testing (Document No. AM-140021-043, AM-YL000336-004) | Low | The new method has been fully validated. | ARD | Completed |
| Analytical method validation readiness | The AM-140021-016 validation protocol is approved and the experiments are pending; The approval of the validation reports (VR) for AM-140021-012, AM-140021-013, and AM-140021-014 is pending; The release analytical methods have been validated; the supplemental validation protocol is currently under review with validation experiment pending, | Low | The validation report will be completed prior to PV step3 starting refer to Change-140021-030105.01 | ARD | Assigned Owner: Yongle Liu Due Date: 11/30/2026 Item status and Closure criteria: complete relevant method validation report |
| Reference Standards | The dimer reference standard is currently under preparation. | Low | Performing HPLC preparative separation. | CMMD | Assigned Owner: Yu Zhang Due Date: 11/30/2026 Item status and Closure criteria: Complete preparation and standardization |
| Sample Preparation and Handling | TSP is in preparation. | Low | The TSP to-do list: TSP-1400210310.01 TSP-1400210311.01 TSP-1400210312.01 | CMMD | Assigned Owner: Yu Zhang Step1：Due Date: 10/20//2026 Step2：Due Date: 11/05//2026 Step3：Due Date: 11/20//2026 |
| Technical Studies |  |  |  |  |  |  |  |  |
| N/A | N/A | N/A | N/A | N/A | N/A |
| Contamination control readiness, |  |  |  |  | Contamination control readiness is in preparation. |  |  |  |  |  |  |  | Low |  |  | The contamination control readiness report RA-1400210301 will be completed prior to manufacturing. |  |  | Production | Assigned Owner: Xuezeng Peng Due Date: 10/30//2026 |
| Validation readiness |  |  |  |  | Validation readiness is in preparation. |  |  |  |  |  |  |  | Low |  |  | The process validation readiness checklist Cpv-CPo140021-030101 Cpv-CPo140021-030201 Cpv-CPo140021-030301 |  |  | CMMD | Assigned Owner: Yu Zhang Step1：Due Date: 10/30//2026 Step2：Due Date: 11/30//2026 Step3：Due Date: 12/30//2026 |
| Nitrosamine Risk Assessment |  |  |  |  | Risk assessment is being conducted through experiments. |  |  |  |  |  |  |  | Low |  |  | Conduct Nitrosamine Risk Assessment and Report Preparation |  |  | CMMD | Assigned Owner: Yu Zhang Due Date: prior to product release Item status and Closure criteria: Completion of Nitrosamine Risk Assessment Report |

Note: *The due dates are established based on the current manufacturing schedule and shall not be later than the actual PPQ initiation date.

# 5. Raw Material Supplier Information

All suppliers of critical raw materials and primary packaging materials must be qualified in accordance with the CMO's Supplier Qualification and Evaluation procedure prior to their use in PPQ batches. The approved supplier list is provided below.

Table 12: The Supplier Information of Raw Material

| Raw Material Name | Material Code (PPQ) | Approved Supplier(s) | Supplier Classification | Supplier Qualification Document No. | Latest Audit Date |
| --- | --- | --- | --- | --- | --- |
| 2-CTC resin | YL003422 | Tianjin Nankai Hecheng S&T Co., Ltd. | Class2 | ADT2026002.V01 | 01/13/2026 |
|  |  | Sunresin New Materials Co.Ltd., GaoLing | Class2 | ADT2026001.V01 | 01/06/2026 |
| Fmoc-Gly-OH | YL004846 | Liaoning Asymchem Laboratories Co., Ltd (FX2). | Class2 | FX2-IA-202501.01 | 12/16/2025 |
|  |  | Asymchem Laboratories (Jilin) Co., Ltd. (DH3) | Class2 | DH3-IA-202501.01 | 10/29/2025 |
|  |  | Chengdu ZY Biochemical Technology Co.,Ltd. | Class2 | ADT2025043.V01 | 12/04/2025 |
| Fmoc-L-Thr(tBu)-OH | YL003563 | Liaoning Asymchem Laboratories Co., Ltd (FX2). | Class2 | FX2-IA-202501.01 | 12/16/2025 |
|  |  | Asymchem Laboratories (Jilin) Co., Ltd. (DH3) | Class2 | DH3-IA-202501.01 | 10/29/2025 |
|  |  | Chengdu ZY Biochemical Technology Co.,Ltd. | Class2 | ADT2025043.V01 | 12/04/2025 |
| Fmoc-L-Ala-OH*H2O | YL006160 | Asymchem Laboratories (Jilin) Co., Ltd. (DH3) | Class2 | DH3-IA-202501.01 | 10/29/2025 |
|  |  | Liaoning Asymchem Laboratories Co., Ltd (FX2) | Class2 | FX2-IA-202501.01 | 12/16/2025 |
|  |  | Chengdu ZY Biochemical Technology Co.,Ltd. | Class2 | ADT2025043.V01 | 12/04/2025 |
| Fmoc-L-Cys(Trt)-OH | YL003565 | Liaoning Asymchem Laboratories Co., Ltd (FX2) | Class2 | FX2-IA-202501.01 | 12/16/2025 |
|  |  | Asymchem Laboratories (Jilin) Co., Ltd. (DH3) | Class2 | DH3-IA-202501.01 | 10/29/2025 |
|  |  | Chengdu ZY Biochemical Technology Co.,Ltd. | Class2 | ADT2025043.V01 | 12/04/2025 |
| Fmoc-L-Asn(Trt)-OH | YL004843 | Asymchem Laboratories (Jilin) Co., Ltd. (DH3) | Class2 | DH3-IA-202501.01 | 10/29/2025 |
|  |  | Chengdu ZY Biochemical Technology Co.,Ltd. | Class2 | ADT2025043.V01 | 12/04/2025 |
| Boc-L-Glu-OtBu | YL008618 | Asymchem Laboratories (Jilin) Co., Ltd. (DH3) | Class2 | DH3-IA-202501.01 | 10/29/2025 |
|  |  | Chengdu ZY Biochemical Technology Co.,Ltd. | Class2 | ADT2025043.V01 | 12/04/2025 |
|  |  | Chengdu ZY Biochemical Technology Co.,Ltd. | Class2 | ADT2025043.V01 | 12/04/2025 |
| ArmorFlex 114 bag with Fill Neck and Chargepoint Discharge | YQ000572 | ILC Dover Poland sp. z o.o. | Class2 | ADT2026007.V01 | 03/11/2026 |

# 6. Personnel

All personnel involved in LSN4182928/ASYM-140021 (step 1 ,step 2  and step3) manufacturing operation sampling, testing, handling, and documentation associated with manufacture of LSN4182928/ASYM-140021  (step 1 ,step 2  and step3)  during the PPQ campaign are trained in accordance with cGMP requirements prior to campaign start-up.

# 7. Cleaning

All equipment to be used for PPQ batch production was cleaned in accordance with the on-site cleaning procedures of the Asymchem. Inspection and QA release were completed prior to use. The synthesis reactor TJ4S-1213-Sy16 was cleaned per document CMa-Sy-TJ401.current; the agitator tank TJ4S-1213-SPS-AT01 & TJ4S-1213-SPS-AT02, TJ4S-1200-AT01 ,TJ4S-1213-AT09  , TJ4S-1213-Tr06 and TJ4S-1213- Tr07 were cleaned per document CMa-Moyable-TJ402.current; The glass-lined reactor TJ4S-1212-R07 and TJ4S-1213-R07 were cleaned per document CMa-Fixed-TJ404.current; The equipment of TJ4S-1213-R03, TJ4S-1213-R12, TJ4S-1213-R14 , TJ4S-1213-R06 TJ4S-1212-FD01, TJ4S-1212-FD02and TJ4S-1212-FD03 were cleaned per document CMa-Fixed-TJ402 current;.

# 8. Storage and Handling Conditions

It is confirmed that the storage conditions applicable to in-process intermediate ASYM-140851 and process intermediate LSN4214882/ASYM-140852 should be storage at 2–8°C and the productLSN4182928/ASYM-140021 should be storage at -25 – -15°C.  The storage conditions will be applied in the PPQ campaign as in the Full Scale non-saleable batch.

# 9. Packaging Materials

The Packaging Materials for LSN4182928/ASYM-140021, Primary is Armor Flex 114 bag with Fill Neck and Charge point Discharge for packaging. Seal the bag using double pull buckle seals. Put it into aluminum foil bag, add pharmaceutical-grade silica gel desiccant between the outer bag of Armor Flex 114 bag with Fill Neck and Charge point Discharge and the aluminum foil bag. Add 3 bags desiccant to each package. Heat seal the aluminum foil bags. And the Outer packaging is HDPE drum, seal with security seal.

It is confirmed that the packaging configuration will be used in the PPQ campaign as in the Full Scale non-saleable batch.

# 10. Conclusion

In summary, for the LSN4182928 / ASYM-140021 technology transfer, no changes are made to the participant team, core synthetic process, raw material supplier information, cleaning procedures, storage and handling conditions, and packaging materials. Multiple optimization items and method adjustments have been identified across raw material control, process operation, equipment facility and analytical method domains, with no critical or major gaps impacting process consistency and product Critical Quality Attributes (CQAs) observed.

The identified adjustments are categorized as follows:

- Raw material control: Raw material specifications are refined and tightened to further strengthen upstream quality control.

- Process operation optimization (Step 1–3): Redundant in-process checks and operations verified unnecessary at full scale are removed; cleavage temperature timing, wash volume and phase separation procedure are optimized; an additional 2-MeTHF solvent chase step is added prior to crystallization. All adjustments aim to improve operational consistency, reduce yield loss and enhance manufacturing efficiency.

- Equipment and automation upgrade: The cleavage reactor thermowell is replaced; a dedicated n-heptane storage tank is added exclusively for Step 3; DCS integration is implemented and supplementary qualification for field instruments is in progress, to improve mixing efficiency, production scheduling efficiency and overall process automation level.

- Analytical method adjustment: The Step 2 residual solvent tracking method (AM-140021-015) and Step 3 reaction monitoring IPC method (AM-140021-016) will be upgraded and fully validated. To resolve the consecutive System Suitability Test (SST) failures observed in Step 2 dried solid sample testing, a new residual solvent method AM-140021-051 with DMI as diluent will be developed, and a formal deviation investigation has been initiated.

All identified adjustments are process optimization, equipment enhancement or method reliability improvement measures, and do not alter the core synthetic route, critical process parameter ranges, IPC acceptance criteria or final product quality specifications. All these changes have no impact on CQAs. All action items have been incorporated into the technology transfer action plan, with each item assigned a defined owner, due date, status, and closure criteria, in accordance with ICH Q9 quality risk management requirements. All analytical method upgrades and validations will be completed prior to PPQ initiation. All outstanding items are managed through the Quality Management System (QMS) for centralized tracking. The corresponding tracking records and supporting evidence will be appended to this document. No adverse impact on PPQ execution or product quality is anticipated.

The remaining TBDs, including residual solvent reporting criteria and validation report effective dates, are captured in the action plan with owners and target dates, and will be completed prior to the relevant PPQ step or use of the method.

# 11. References

ICH Q3C (R8) — Residual Solvents

ICH Q3D — Elemental Impurities

ICH Q7 — Good Manufacturing Practice for APIs

Equipment Suitability Assessment Report: RA-140021030102.01

Equipment Suitability Assessment Report: RA-140021030201.01

Equipment Suitability Assessment Report: RA-140021030301.01

Cleaning Impact Assessment: Reference document number: CMa-Sy-TJ401.01, CMa-Moyable-TJ402.03, and CMa-Fixed-TJ404.01.

CMO Supplier Qualification Procedure: SOP-MM-046

# 12. Appendix I Risk Mitigation Measures/Action Plan Tracking Table

Table 13: The tracking table of mitigation measure/action

| Area Evaluated |  | Gap / Difference |  |  | Risk to product CQAs |  | Action Plan |  | Owner (Function) |  | Milestone* |  |  | Completion Evidence |  |  | Signature/Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Process and Equipment |  |  |  |  |  |  |  |
| Process |  | The post-cleavage rinse volume is increased from 5 volumes to 8 volumes |  |  | Low |  | Relevant contents have been filled in Change-CPo140021-030202.01 |  | CMMD |  | Assigned Owner: Yu Zhang Due Date: 11/05/2026 Item status and Closure criteria: Change control sign-off |  |  |  |  |  |  |
| Process |  | Revised per Manufacturing Operation Record |  |  | Low |  | This update was implemented upon joint discussion and confirmation among Production, Customer, QAN/A |  | CMMD |  | Assigned Owner: Yu Zhang Due Date: 10/22/2026 Item status and Closure criteria: Change control sign-off |  |  |  |  |  |  |
| Process |  | The process understanding, historical manufacturing experience, CPP rationale and control strategy knowledge have not been transferred and implemented |  |  | Medium |  | Documented training will be provided to the involved personnel prior to PPQ production initiation. |  | CMMD |  | Assigned Owner: Yu Zhang Due Date: 10/22/2026 Item status and Closure criteria: Complete the training. |  |  |  |  |  |  |
| Process |  | MOR is in preparation. |  |  | Low |  | The MOR to-do list: MOR-TJ414002101 MOR-TJ414002102 MOR-TJ414002103 |  | CMMD |  | Assigned Owner: Yu Zhang Step1：Due Date: 10/20//2026 Step2：Due Date: 11/05//2026 Step3：Due Date: 11/20//2026 |  |  |  |  |  |  |
| Equipment |  | Step3:Add the new tank to storage n-heptane |  |  | Low |  | Use dedicated n-heptane tank TJ4S-1213-Tr07 for Step3 PPQ; complete equipment suitability assessment (RA-140021030301.01). |  | CMMD |  | Assigned Owner: Yu Zhang Due Date: 11/20//2026 Item status and Closure criteria: ESA sign-off |  |  |  |  |  |  |
| Equipment |  | Replace an new thermowell |  |  | Low |  | Replace the thermowell of reactor TJ4S-1212-R07; perform equipment re-validation and engineering re-assessment after replacement. |  | Production |  | Assigned Owner: Hui Ma Due Date: 10/22/2026 Item status and Closure criteria: complete equipment re-validation and engineering re-assessment |  |  |  |  |  |  |
| Equipment | For equipment automation upgrade | Low | Complete DCS integration; finish supplementary qualification of field instruments; perform required equipment re-validation / engineering assessment for modified/added equipment. | Production | Assigned Owner: Hui Ma Due Date: 10/22/2026 Item status and Closure criteria: complete equipment re-validation and engineering re-assessment |  |  |
| ESA | The step 2 Equipment suitability assessment(RA-140021030201.01) is not yet finalized. | Medium | Finalize and sign off the Equipment suitability assessment report(RA-140021030201.01) | CMMD | Assigned Owner: Yu Zhang Due Date: 11/05/2026 Item status and Closure criteria: ESA sign-off |  |  |
|  | The step 3 Equipment suitability assessment(RA-140021030301.01) is not yet finalized. |  | Medium |  |  | Finalize and sign off the Equipment suitability assessment report (RA-140021030301.01) |  | CMMD |  | Assigned Owner: Yu Zhang Due Date: 11/20/2026 Item status and Closure criteria: ESA sign-off |  |  |  |  |  |  |
| Cleaning Validation |  |  |  |  |  |  |  |
| Cleaning Validation |  | Cleaning validation gaps identified for product-dedicated equipment: cleaning validation status, carryover limits based on toxicology/PDE, and analytical method for swab/rinse testing. |  |  | Medium |  | Develop appropriate cleaning methods during PPQ; establish toxicology/PDE-based carryover limits; perform cleaning testing per DS-GMP-003 and DS-GMP-043. |  | CMMD |  | Assigned Owner: Yu Zhang Due Date: 11/20/2026 Item status and Closure criteria: CVP sign-off |  |  |  |  |  |  |
| Analytical method readiness |  | As the cleaning solvent needs to be changed to process solvent, the cleaning detection methods for Steps 2 and 3 need to be re-developed and re-validated |  |  | Medium |  | Method development and validation will be initiated as soon as possible. |  | QC |  | Assigned Owner: Haini Wang Due Date: 11/20/2026 Item status and Closure criteria: complete the cleaning detect method validation |  |  |  |  |  |  |
| Materials |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Seed material specification |  | Differentiated control shall be implemented for seeding material and corresponding bulk materials, with dedicated independent material codes assigned for seeding crystal to achieve distinction. For detailed control requirements, refer to seeding material control procedure for LSN4182928/ASYM-140021 |  |  | Low |  | Relevant contents have been filled in Change-140021-030304.01 |  | ARD |  | Assigned Owner: Yongle Liu Due Date: 11/20/2026 Item status and Closure criteria: complete equipment re-validation and engineering re-assessment |  |  |  |  |  |  |
| QC & Contract Labs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Analytical Methods – Step 2 Residual Solvent |  | A gap was identified for residual solvent testing method for IPC dried solid samples of Step 2 cleavage. During full-scale non-saleable batch campaign, three consecutive SST failures were observed for method AM-140021-015.06, n-heptane recovery (90%) out of 95–105% acceptance criteria. Deviation investigation initiated per site procedure. |  |  | Low |  | Implement new residual solvent method AM-140021-051 (using DMI as diluent) for PPQ campaign based on feasibility & development studies to resolve SST failure. |  | ARD |  | Assigned Owner: Yongle Liu Due Date: 11/05/2026 Item status and Closure criteria: complete the new method validation report |  |  |  |  |  |  |
| Analytical Methods – Step 3 Reaction Monitoring IPC |  | Step3 stage2 reaction mixture: saleable batches monitor both ASYM-140852 and ASYM-141266 by IPC method AM-140021-016; PPQ removes ASYM-141266 from IPC scope. ASYM-141266 is unstable at room temperature and quickly converts to ASYM-140852, leading to unreliable quantitative IPC results. |  |  | Low |  | Optimize Step3 stage2 IPC strategy. Remove ASYM-141266 from routine IPC testing; retain ASYM-140852 IPC testing. |  | ARD |  | Assigned Owner: Yongle Liu Due Date: 11/20/2026 Item status and Closure criteria: complete relevant method validation report |  |  |  |  |  |  |
| Analytical method validation readiness |  | The AM-140021-016 validation protocol is approved and the experiments are pending; The approval of the validation reports (VR) for AM-140021-012, AM-140021-013, and AM-140021-014 is pending; The release analytical methods have been validated; the supplemental validation protocol is currently under review with validation experiment pending, |  |  | Low |  | The validation report will be completed prior to PV step3 starting refer to Change-140021-030105.01 |  | ARD |  | Assigned Owner: Yongle Liu Due Date: 11/30/2026 Item status and Closure criteria: complete relevant method validation report |  |  |  |  |  |  |
| Reference Standards |  | The dimer reference standard is currently under preparation. |  |  | Low |  | Performing HPLC preparative separation. |  | CMMD |  | Assigned Owner: Yu Zhang Due Date: 11/30/2026 Item status and Closure criteria: Complete preparation and standardization |  |  |  |  |  |  |
| Sample Preparation and Handling |  | TSP is in preparation. |  |  | Low |  | The TSP to-do list: TSP-1400210310.01 TSP-1400210311.01 TSP-1400210312.01 |  | CMMD |  | Assigned Owner: Yu Zhang Step1：Due Date: 10/20//2026 Step2：Due Date: 11/05//2026 Step3：Due Date: 11/20//2026 |  |  |  |  |  |  |
| Technical Studies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contamination control readiness, |  | Contamination control readiness is in preparation. |  |  | Low |  | The contamination control readiness report RA-1400210301 will be completed prior to manufacturing. |  | Production |  | Assigned Owner: Xuezeng Peng Due Date: 10/30//2026 |  |  |  |  |  |  |
| Validation readiness |  | Validation readiness is in preparation. |  |  | Low |  | The process validation readiness checklist Cpv-CPo140021-030101 Cpv-CPo140021-030201 Cpv-CPo140021-030301 |  | CMMD |  | Assigned Owner: Yu Zhang Step1：Due Date: 10/30//2026 Step2：Due Date: 11/30//2026 Step3：Due Date: 12/30//2026 |  |  |  |  |  |  |
| Nitrosamine Risk Assessment |  | Risk assessment is being conducted through experiments. |  |  | Low |  | Conduct Nitrosamine Risk Assessment and Report Preparation. |  | CMMD |  | Assigned Owner: Yu Zhang Due Date: prior to product release Item status and Closure criteria: Completion of Nitrosamine Risk Assessment Report |  |  |  |  |  |  |

Note: *The due dates are established based on the current manufacturing schedule and shall not be later than the actual PPQ initiation date.