## Action Tracker
Number | Category | Action Item | Implementation Timing | Implementation Effort | Proposed target completion date | Existing approach | Action Plan | Questions | Lilly Response | Scope | Status | Notes | Asymchem Lead Owner | Lilly QA
1 | BLA/technical | Cleaning validation and verification strategy needs presented. Including: strategy for determining appropriate cleaning solution and conditions (time, temp etc), how these are tranlasted to the operational record to ensure proper execution in a repeatable manner. Additionaly need to share how small parts and manual cleaned components are managed and integrated into cleaning records. Additionally, how are rinse and swab limits, sampling instructions, and results recorded. | Prior to Pre-PPQ | High > 1 month | Manual Cleaning Procedure step1: 10/07/2026 step2: 10/20/2026 step3A: 11/09/2026 step3B: 11/28/2026 | -- | The cleaning validation and verification strategy was discussed with the customer on September 25, 2026. Dedicated cleaning SOPs and master batch cleaning records will be prepared for each step prior to Pre-PPQ. An example will be provided to customer for review ASAP. | -- | Need to align on cleaning interval length for each step which will establish frequency of "major" cleaning. When an interval is applied, what is the strategy for hold duration between batches within an interval? When will the cleaning master batch record be required for SPPS? After first batch? This may drive the timeline and ugency for alignement on cleaning strategy and documentation. Until this is developed what instructions will Asymchem use to complete appropriate cleaning between Step 3 demo and PPQ start to ensure the equipment is sufficiently clean? What cleaning record was executed after Step 1/Step 2 Demo - can we review this? Please ensure that cleaning SOPs/records are inclusive of any product contact misc. component cleaning required (filter housings, pumps, etc.) that may not be readily cleaned by CIP cycle. Also, for each step, please point us to where rinse/swab limit calculations exist so we can review these. Additionally, please specify how many cleaning verification vs. validation runs will be executed and when cleaning validation will be started (with respect to PPQ) for each step. 需要就各步骤的清洁间隔长度达成一致，这将决定“大清洁”的频次。采用清洁间隔时，同一间隔内批与批之间的保持时间采用什么策略？ SPPS 何时需要清洁主批记录？第一批之后吗？这可能决定清洁策略和文件对齐的时间表及紧迫程度。在该记录完成之前，Asymchem 将依据什么指令在 Step 3 Demo 与 PPQ 开始之间完成适当的清洁，以确保设备足够洁净？Step 1/Step 2 Demo 之后执行的是哪份清洁记录？我们能否审阅？ 请确保清洁 SOP/记录涵盖所有需要清洁的产品接触类零散部件（过滤器外壳、泵等），这些部件可能无法通过 CIP 程序有效清洁。 另外，请针对每个步骤告知淋洗/擦拭限度的计算在哪里，以便我们审阅。此外，请说明每个步骤将分别执行多少次清洁确认（verification）和清洁验证（validation），以及清洁验证何时开始（相对于 PPQ 的时间节点）。 | All Steps | Open | The team feels we need to have confidence that Asymchem can adequately clean equipment prior making saleable GMP material | Production / Yanlong Li 生产/李延龙 | QA / Weijiang Liu QA/刘维江
2 | Technical | Install or verify nameplate on rupture disk | Prior to Demo | Low < 1 week | 2026-09-27 | -- | Please refer to the slides ( link in Column L) | -- |  | Purification | Completed | Asymchem_Visit_Action_Tracker_Partial Feedback_09-29-2026.pptx | Production / Yanlong Li 生产/李延龙 | N/A
3 | Technical | Confirm inlet line sizing meets the 200 L/h process requirement | Prior to Demo | Low < 1 week | 2026-09-30 | -- | Theoretical calculation by IEPE; on-site testing. Please refer to the slides ( link in Column L) | -- | AJM: Acceptable. Consider point closed. AJM：可以接受，此项视为关闭。 | Purification | Open | Asymchem_Visit_Action_Tracker_Partial Feedback_09-29-2026.pptx | Production / Linchong Liu 生产/刘林冲 | N/A
4 | BLA | During field walkthroughs several lines visual appeard slopped in undesired location. Confirm all lines are sloped (including flexible hoses) to appropriate low points with proper drain point. | Prior to Pre-PPQ | Med > 1 week < 1 Month | Option 1: No CIP. Equipment connections meet 2D requirement; transfer piping section does not meet 3D requirement. Disassembly cleaning will be required afterwards. Completion date: 12/17/2026 Option 2: No CIP. Equipment connections meet 2D requirement with CIP ports reserved. Most of the transfer piping meets 2D requirement and minimum 3D requirement. Completion date: 01/20/2027 Option 3: In-line CIP. The vessel and piping are designed entirely following the 2D design philosophy. Completion date: 04/25/2027 | Modification and installation of the C3 and C4 lines are complete, and slope verification is in progress. The C1 and C2 lines were previously assessed as having no slope requirement, and only drain points were provided; the slope requirement needs to be re-discussed and confirmed. | Assess and inspect each process step and each line individually. | The requirement for the C1 and C2 lines is drainability, with no specific slope requirement. How should the slope be confirmed? | Need further discussion to clarify Asymchem's proposed options. Not sure we are following what the Options in column F mean. 需要进一步讨论，以澄清 Asymchem 提出的方案。我们不太理解 F 列中各 Option 的含义。 | All Steps | Open |  | Engineering / Hongjie Guo Production / Junfeng Zhang 工程/郭宏杰 生产/张俊峰 | QA / Meijia Liu QA/刘美佳
5 | Technical | Missing sight-glass lights | Post PPQ | Med > 1 week < 1 Month | 2026-12-30 | The entire equipment train is being reviewed; any missing sight-glass lights will be procured. | An inspection checklist is being established. | -- | Please ensure insructions are provided in MOR to use flashlights as needed to complete visual inspections inside tanks in the interim. 过渡期内，请确保在 MOR 中写明指令：必要时使用手电筒完成罐内目视检查。 | All Steps | Open | Interim measure recommended to use flashlights through sight glasses to perform visual inspections | Engineering / Hongjie Guo 工程/郭宏杰 | N/A
6 | Technical | Review HCl charging dip-tube arrangement and confirm material of construction | Prior to Demo | Low < 1 week | 2026-10-03 | -- | Provide the material-of-construction certificate and adjust(shorten) the current dip-tube length. | -- | AJM: Sounds good. For diptube, if adding above surface, make sure that flow is directed into liquid heel of tank and not towards any surfaces. If using sub-surface, ensure that you can prevent non-homogenity concerns in line. For material, if using PTFE, consider impacts of permeation - consider PFA as alternative. AJM：好的。关于插底管：如在液面上方加入，请确保液流导向罐底存液，而不是冲向任何表面；如采用液面下加入，请确保能够避免管线内的不均匀问题。材质方面，如使用 PTFE，请考虑渗透的影响，可考虑以 PFA 作为替代。 | Purification | Open | Source note suggests HC; confirm exact alloy/specification | IEPE / Mingzhi Zheng Production / Xingtao Fan IEPE/郑明智 生产/范兴涛 | QA / Qi Wang QA/王琪
7 | Technical | Update MOR or SOP to require mobile-scale reading after the peristaltic pump empties the flexible connection | Prior to Demo | Low < 1 week | 2026-10-03 | -- | Update the MOR to include the detailed requirement. | -- | AJM: No additional follow up needed if consifrmed in MOR. Just want to ensure enough detail is present to ensure that we accurately account for what made it into the tank. AJM：如已在 MOR 中确认，则无需进一步跟进。我们只是希望记录中有足够的细节，确保能够准确核算实际进入罐内的物料。 | Purification | Open | Follow up with Peter to clarify this item | Production / Yanlong Li 生产/李延龙 | QA / Qi Wang QA/王琪
8 | Technical | Observed waste header from process without check valves. Assess process piping connections for back flow risk and install check valves as necessary | Prior to Pre-PPQ | Med > 1 week < 1 Month | 2026-11-03 | -- | To be carried out together with the overall piping construction for step 3 | -- | Please evaluate steps 1 and 2 rigs to confirm if similar gaps exist 请评估 Step 1 和 Step 2 的设备装置，确认是否存在类似差距。 | All Steps | Open |  | Production / Yanlong Li 生产/李延龙 | N/A
9 | BLA | CNC raw material staging area lacks appropriate controls. Evaluate options and implement short term safeguards to reduce risk associated with the lack of a CNC material-flow buffer zone and differential-pressure interlock in Workshop 12 CNC | Prior to Pre-PPQ | Med > 1 week < 1 Month | 2026-10-20 | -- | Submit the change control document to carry out renovation on the factory logistics passage. An airlock will be added before raw materials are transferred into the CNC area. | -- | Need to propose and implement short term administrative controls to address this gap until the long term facility modificaition can be made 在长期厂房改造完成之前，需要提出并实施短期管理控制措施来弥补这一差距。 | All Steps | Open |  | Engineering / Hongjie Guo Production / Hui Ma 工程/郭宏杰 生产/马辉 | QA / Meijia Liu QA/刘美佳
10 | Technical | Justify the one-month service life for dedicated PW hoses | Post PPQ | Low < 1 week | 2026-12-30 | One-month service life for dedicated PW hoses. | Perform a use/disinfection-period study on dedicated PW hoses and redefine their lifecycle. | -- |  | All Steps | Open | Is 1 month replacement too conservative? Could lifetime be extended? What was basis for 1 month replacement frequency? | Production / Chunpeng Hu 生产/胡春鹏 | QA / Xiong Xiong QA/熊熊
11 | BLA/technical | Review lifecycle management for dedicated product contact and solvent hoses. Recommend visual inspection of hoses with some frequency regardless of campaign length. | Prior to Pre-PPQ | Low < 1 week | step1: 10/07/2026 step2: 10/20/2026 step3A: 11/09/2026 step3B: 11/28/2026 | -- | Revise the SOP to define the corresponding requirements. | -- | No additional follow up required. However, please ensure spare hoses are on order/in hand for critical hoses in the event a replacement is needed. 无需进一步跟进。但请确保关键软管的备用软管已下单或已到货，以备需要更换时使用。 | All Steps | Open |  | Production / Kai Liu 生产/刘凯 | QA / Xiong Xiong QA/熊熊
12 | BLA/technical | Review pre-use cleaning for solvent transfer and process-solution transfer hoses. Current practice to rinse new product contact hoses with methanol followed by water and dry with nitrogen after 1st installation. Recommend using process solvent in place of water and methanol. | Prior to Demo | Med > 1 week < 1 Month | 2026-10-05 | -- | Hoses have completed cleaning. A solvent run is planned prior to Step3 Demo production. After completion of the solvent run, the hoses will be cleaned with process solvent. | -- | Update procdure to ensure future new hose installations are rinsed with solvent prior to use (Not water/methanol as last fuild through the hose prior to use in the process) 请更新程序，确保今后新安装的软管在使用前用溶剂冲洗（在用于工艺之前，最后流经软管的不应是水/甲醇）。 | All Steps | Open | Prevent contamination of demo batch that could impact representativeness. | Production / Yanlong Li Linchong Liu 生产/李延龙 刘林冲 | QA / Weijiang Liu QA/刘维江
13 | BLA | Curently site uses corrugated hoses for process and solvent transers. Upgrade to smooth-bore internal design, considering Pharmaline N hoses. | Prior to Pre-PPQ | Med > 1 week < 1 Month | 2026-11-30 | Platinum-cured silicone hoses are used. | Replacement is planned. | -- | Intent is to replace with smooth bore hoses prior to PPQ start for each step. If not possible please specify where corrugated will be used in the short term. Please clarify the MOC of process/solvent contacting hoses. Are they silicone? We were under the impression they were PTFE and only water hoses were silicone. 预期是在各步骤 PPQ 开始前更换为光滑内壁软管。如无法做到，请说明短期内哪些位置仍将使用波纹软管。请说明接触工艺液/溶剂的软管材质（MOC）。是硅胶吗？我们原先的理解是这些软管为 PTFE 材质，只有水管是硅胶的。 | All Steps | Open | Effort is dependent on lead time for new hoses | Production / Yanlong Li 生产/李延龙 | QA / Zhiqiang Sun QA/孙志强
14 | Impurity Investigation | Review supplier options for reliable sourcing of DIPEA containing less than 50 ppm acetaldehyde | Prior to Pre-PPQ | Med > 1 week < 1 Month | Discuss separately | -- | -- | -- |  | SPPS | Open |  | Project Team / Xinyi Zhu 项目组/朱新义 | N/A
15 | Impurity Investigation | Complete evaluation of internal DIPEA processing options to further reduce acetaldehyde content | Prior to Pre-PPQ | Med > 1 week < 1 Month | Discuss separately | -- | -- | -- |  | SPPS | Open |  | Project Team / Xinyi Zhu 项目组/朱新义 | N/A
16 | Impurity Investigation | Evaluate options to reduce DIPEA exposure time during washing steps (such as larger DIPEA containers and/or addition of a larger dedicated makeup tank) | Prior to Pre-PPQ | Low < 1 week | Discuss separately | -- | -- | -- |  | SPPS | Open |  | Project Team / Xinyi Zhu 项目组/朱新义 | N/A
17 | Impurity Investigation | Evaluate feasability to increase nitrogen sparge rates for SC coupling to reduce HCN concentration. Confirm equipment limitations and establish the qualified operating envelope for higher nitrogen sparging rates | Prior to Pre-PPQ | Low < 1 week | Discuss separately | -- | -- | -- |  | SPPS | Open | Current equipment reportedly supports up to ~40 m³/h; current operating limit ~20 m³/h | Project Team / Xinyi Zhu 项目组/朱新义 | N/A
18 | Impurity Investigation | Assess feasibility and effectiveness of nitrogen sweep operation during SC coupling to reduce HCN concentration. | Prior to Pre-PPQ | Low < 1 week | Discuss separately | -- | -- | -- |  | SPPS | Open |  | Project Team / Xinyi Zhu 项目组/朱新义 | N/A
19 | Impurity Investigation | Complete planned passivation of GG917 and LAARA process lines. Confirm there are not similar gaps on cleavage and purification process lines for GG917 steps. | Prior to Pre-PPQ | Low < 1 week | L1 Step 1 Completed; Step 2: 10/06/2026 L2 Step 1 Completed; Step 2: 10/06/2026 L3 Step 1 Completed; Step 2: 10/06/2026; Step 3: 10/08/2026 GG917 Step 1 Completed; Step 2: 10/05/2026; Step 3: Completed | No passivation on the inner surface of process lines. | Perform passivation of GG917 and LAARA process lines. | -- | No additional follow up needed on approach. However, please clarify the difference between the two "Step 3"'s provided in column F. 对该方案无需进一步跟进。但请说明 F 列中两个“Step 3”的区别。 | All Steps | Open |  | Production / Zhongyao Zhang, Fan Wang 生产/张忠尧、王帆 | QA / Mingyang Yang QA/杨明旸
20 | Impurity Investigation | Provide a remediation plan and timeline for passivation of all bulk solvent tanks and headers | Prior to Pre-PPQ | High > 1 month | 2027-02-17 | The Phase I tank farm will not be passivated for now; metal-ion testing is performed instead. | After the Phase II tank farm is handed over, its lines and tanks will be passivated, and all subsequent projects will use solvents from the Phase II tank farm. | -- | Further discussion needed on strategy to address concerns with unpassivated solvent header tanks, piping, and weld quality based on obsvervations from recent deviation. How long would it take to passivate solvent headers and/or inspect a subset of welds for rust via visual inspection or boroscope? Was the weld involved in the residue investigation a hand weld? 基于近期偏差中的观察，需要进一步讨论如何应对未钝化的溶剂高位槽、管道以及焊接质量方面的问题。钝化溶剂总管和/或通过目视检查或内窥镜抽查部分焊缝是否生锈，需要多长时间？残留物调查中涉及的焊缝是否为手工焊？ | All Steps | Open |  | Tank Farm / Wenyi Zhang 罐区/张文艺 | QA / Meijia Liu QA/刘美佳
21 | Impurity Investigation | Implement administrative controls for raw material receipt and transfer into CNC areas to minimize potential exposure to outdoor conditions. | Prior to Pre-PPQ | Med > 1 week < 1 Month | 2026-10-20 | There is an administrative requirement that, once material arrives at the production workshop, a dedicated operator must transfer it to the CNC area. | Update the SOP to include detailed material lifecycle management to avoid gaps during material transfer. | -- | To be clear, our expectation would be that there should be specific recording of time received at the outdoor dock and time moved into building by Operations. This will provide traceability with respect to how long material was exposed to outdoor conditions. Time outdoors should be minimized. 需要明确的是，我们的期望是由生产部门专门记录物料在室外卸货区的接收时间及转入厂房的时间。这样可以追溯物料暴露于室外环境的时长。物料在室外的时间应尽量缩短。 | All Steps | Open |  | Production / Hui Ma 生产/马辉 | QA / Zhiqiang Sun QA/孙志强
22 | BLA | Define long-term facility modifications to provide an airlock or physical segregation for transer of raw materials into CNC area for stagging. | Post PPQ | High > 1 month | 2026-10-20 | -- | Submit the change control document to carry out renovation on the factory logistics passage. An airlock will be added before raw materials are transferred into the CNC area. | -- | No additional follow up. 无需进一步跟进。 | All Steps | Open |  | Engineering / Hongjie Guo Production / TBD 工程/郭宏杰 生产/ | QA / Meijia Liu QA/刘美佳
23 | BLA | Complete review of the site multiproduct cross-contamination risk assessment and incorporate high level summary of risk and mitigations into the process specific CCS docments for each process steps | Prior to Pre-PPQ | Med > 1 week < 1 Month | 2026-10-20 | The CCS document lacks a detailed description. | Add a detailed description to the CCS document. | -- | JOB: Lilly will review CCS and provide feedback JOB：Lilly 将审阅 CCS（污染控制策略）并提供反馈。 | All Steps | Open |  | QA / Qi Wang QA/王琪
24 | Technical | Replace silicone water hoses with PTFE hoses or provide a documented technical justification | Post PPQ | Med > 1 week < 1 Month | 2026-11-30 | Silicone water hoses are currently used. | Replace silicone hoses with PTFE hoses. | -- | No additional follow up. 无需进一步跟进。 | Purification | Open | Silicone could pose risk to process if shedding occurs as PTFE is inherient and more inert | Production / Chunpeng Hu 生产/胡春鹏 | QA / Xiong Xiong QA/熊熊
25 | BLA | Update procedure to ensure immediate water hose disconnection and controlled storage after use | Prior to Demo | Med > 1 week < 1 Month | 10/04/2026 | No clear time requirement in the SOP for disconnecting water hoses after use. | Update the SOP to require that water hoses be disconnected immediately once water charging is finished. | -- | AJM: Additionally, please confirm that when water hose connections are made that draining of the hose after use is considered to prevent water from getting on equipment/floor during disconnection. AJM：另外，请确认在连接水管时已考虑使用后排空软管，以防断开连接时水洒到设备/地面上。 | Purification | Open | Prevent biofilm formation during Demo processing that could impact PPQ. | Production / Kai Liu 生产/刘凯 | QA / Xiong Xiong QA/熊熊
26 | BLA | Update CCS for each process step to clearly define the filtration strategy in alignment with the corporate filtration gudiance. Include filtration location, type, replacement criteria, justification and diagrams or tables to CCS documentation for each process step | Prior to Pre-PPQ | Med > 1 week < 1 Month | 2026-10-11 | The detailed filtration principle is not included in CCS document. | Update CCS document to include the detailed filtration principle. | -- | AJM: Please provide an example of what this will look like at your earliest convinence for feedback from the Lilly team. In the example, please include a variety of filter types (particualte control only, bioburden control, raw material/utility, etc.), so we can provide meaningful feedback. AJM：请尽早提供一份示例，说明最终的形式，以便 Lilly 团队提供反馈。示例中请涵盖多种过滤器类型（仅用于颗粒控制、用于微生物负荷控制、原料/公用工程等），以便我们给出有意义的反馈。 | All Steps | Open |  | Project Team / Xinyi Zhu 项目组/朱新义 | QA / Shenghui Yu QA/于生辉
27 | BLA | Filtration of liquid raw materials is required for all process steps. Reassess and document justification for 75-micron filtration of SPPS raw material drum charging. | Prior to Demo | Med > 1 week < 1 Month | 2026-10-04 | No aglined requirement for liquid material filtration. | Update MOR to 10-micron. | -- | AJM: Please confirm that this applies to all raw material charges throughout the process (Step 1, 2, 3A/3B). 10 micron is more reasonable but still not consistent with guidance that you shared for other particualte control filters (0.45 micron per your other guidance). On site we had discussed using something like the Parker ZCTP1-045C-N-PP Fluroplus filter - is there a reason you elected to go away from this? AJM：请确认这适用于整个工艺中的所有原料投料（Step 1、2、3A/3B）。10 微米更为合理，但仍与你们分享的其他颗粒控制过滤器的指南不一致（按你们另一份指南为 0.45 微米）。现场我们曾讨论使用类似 Parker ZCTP1-045C-N-PP Fluroplus 的过滤器，你们决定不采用该方案是出于什么原因？ | All Steps | Open | Prevent particulate contamination of equipment which may impact PPQ (particualte can be challenging to remove once introduced). | Production / Fan Wang 生产/王帆 | QA / Shenghui Yu QA/于生辉
28 | BLA | Revise glovebox cleaning practices to use approved alcohol wipes rather than water wipes in dispensing areas. | Prior to Demo | Low < 1 week | 2026-10-04 | Water is used for glovebox cleaning. | After water cleaning, an IPA wipe shall be performed to avoid any water residue. | -- | AJM: No additional concern. JOB: Do we have solubility data to support water and IPA wipes removing potential residual material? Or, is visually clean the only control? AJM：没有其他顾虑。 JOB：我们是否有溶解度数据，支持用水和 IPA 擦拭能够去除潜在的残留物料？还是说目视洁净是唯一的控制手段？ | All Steps | Open |  | Production / Kai Liu 生产/刘凯 | QA / Zhiqiang Sun QA/孙志强
29 | BLA | Complete planned upgrades and demonstrate CNC area relative humidity remains below 60% during summer conditions | Post PPQ | High > 1 month | 2027-05-30 | The current humidity control capability of the air conditioning system meets requirements. As winter is approaching, the outdoor ambient temperature and humidity will be low, and the existing system can satisfy humidity control requirements. Modification is planned to be completed before the arrival of high-temperature and high-humidity conditions in summer 2027, to ensure that the system can still meet the humidity control specifications after modification under summer operating conditions. | Modify the air handling units by adding cooling coils, and complete qualification during a production gap. | -- | No additional follow up. Consider point closed. 无需进一步跟进，此项视为关闭。 | All Steps | Open | Confirm procedure in place to use protable dehumidifiers in the short term until all upgrades are complete to allow for robust control iof humidity in CNC areas. | Production Equipment Dept. / Wenyi Zhang 生产设备部/张文艺 | QA / Meijia Liu QA/刘美佳
30 | BLA | Asymchem to provide vent header drawings and designs to Lilly for review. | Prior to Demo | Low < 1 week | 2026-09-28 | Has been provided. | -- | -- |  | All Steps | Completed |  | Engineering / Hongjie Guo IEPE / Guorui Zhang 工程/郭宏杰 IEPE/张国睿 | QA / Meijia Liu QA/刘美佳
31 | BLA/technical | Evaluate process-specific cross-contamination risks from process connections and utility lines, then develop a long-term plan to isolate nonessential connections or otherwise mitigate identified risks. Assess shared-utility and equipment-isolation requirements for GG917 and LAARA operations | Prior to Demo | Med > 1 week < 1 Month | 2026-10-04 | No detailed assessment in the CCS document. | Add a detailed assessment to the CCS document. | -- | Is there a general procedure/process in place that describes Asymchems approach to changeover and segregation practices? JOB: Lilly will review CCS and provide feedback 是否有通用的程序/流程，描述 Asymchem 在换产和隔离方面的做法？ JOB：Lilly 将审阅 CCS（污染控制策略）并提供反馈。 | All Steps | Open |  | Production / Linchong Liu 生产/刘林冲 | QA / Qi Wang, Mingyang Yang QA/王琪，杨明旸
32 | BLA | Implement the use of permeable film to cover the ends of process and water hoses while stored for drying | Prior to Demo | Med > 1 week < 1 Month | 2026-10-04 | No permeable film is used to cover the ends of process and water hoses. | Use permeable film to cover the ends of process and water hoses. | -- | Confirm that permeable films are compatable with all process/solvent solutions. If not, and the process/solvent is non-growth promoting, use clean, solid cap instead. 请确认透气膜与所有工艺液/溶剂均相容。如不相容，且工艺液/溶剂不促进微生物生长，请改用洁净的实心盖。 | All Steps | Open | Prevent hose contamination during Demo processing that could impact PPQ. | Production / Chunpeng Hu 生产/胡春鹏 | N/A
33 | BLA | Install low-point drains on the inlet and outlet of all PD pumps used in Category 4 systems, and add pre- and post-cleaning steps to drain from these points and nitrogen-purge through the pump to the outlet drain | Prior to Pre-PPQ | Med > 1 week < 1 Month | 2026-10-20 | This capability is already in place. | Prepare a checklist to include pre- and post-cleaning steps. | -- | AJM: Please confirm low-point drains on both sides of PD pumps are present. AJM：请确认 PD 泵（容积泵）两侧均设有低点排放口。 | Purification | Open |  | Production / Yanlong Li, Kai Liu 生产/李延龙，刘恺 | QA / Weijiang Liu QA/刘维江
34 | BLA | Update the cleaning program for PD pumps so recovery factors account for large-area soft parts and include a representative pump swab location for product-contact applications | Prior to Pre-PPQ | Med > 1 week < 1 Month | 2026-11-10 | The PD pump is rinse-sampled for residue testing. | Update the SOP to include swab sampling for residue testing. | -- | No additional follow up needed. 无需进一步跟进。 | Purification | Open |  | Production / Kai Liu 生产/刘凯 | QA / Meijia Liu QA/刘美佳
35 | BLA | Evaluate long-term replacement of PD pumps with pressure transfer or hygienic centrifugal pumps with low-point casing drains; where PD pumps remain necessary, assess more drainable designs | Post PPQ | High > 1 month | 2027-01-30 | After use, both ends of the pump are drained and blown dry; a detailed operating procedure will be provided. | The corresponding hygienic centrifugal pumps are being procured. | -- | No additional follow up needed. 无需进一步跟进。 | All Steps | Open |  | Engineering / Hongjie Guo Production / Junfeng Zhang 工程/郭宏杰 生产/张俊峰 | QA / Meijia Liu QA/刘美佳
36 | BLA | Several non-compliant items still exist against equipment/piping standards. For example, ball valves on Category 4 equipment/piping, for all steps long tank nozzles on vessel heads and/or branches off tank nozles that will not be cleanable during CIP, diptubes supported by hooks that form crevices, missing drains at low points (especially around filters), non-hygienic/cleanable instrument designs (level, temperature), flow meters installed in non-drainable, flanged connections on category 3 and 4 equipment/piping, bolted agitator blades, deadlegs in various locations due to use of non-zero-static valving/non-minimum distance tees, etc. Conduct a comprehensive gap assessment against equipment and piping standards and prioritize remediation of high-risk Category 3 and 4 systems before production start | Prior to Pre-PPQ | High > 1 month | Option 1: No CIP. Equipment connections meet 2D requirement; transfer piping section does not meet 3D requirement. Disassembly cleaning will be required afterwards. Completion date: 12/17/2026 Option 2: No CIP. Equipment connections meet 2D requirement with CIP ports reserved. Most of the transfer piping meets 2D requirement and minimum 3D requirement. Completion date: 01/20/2027 Option 3: In-line CIP. The vessel and piping are designed entirely following the 2D design philosophy. Completion date: 04/25/2027 | N/A | Redesign is in progress. Once the design is confirmed, the key items will be discussed with the Lilly team before execution. |  | AJM: Please explain what the Options in COlumn F mean in more details. Please share videos of progress when possible for Lilly to visually confirm acceptability. Also, where needed, please send design drawings for our confirmation before installing in field. I am most interested for how you are going to overcome the non-ideal instruments like the level transmitters and temperature elements as these are less straightforward to me than some of the other items. AJM：请更详细地解释 F 列中各 Option 的含义。如有可能，请分享进展视频，以便 Lilly 直观确认是否可接受。另外，如有需要，请在现场安装前发送设计图纸供我们确认。我最关心的是你们将如何解决液位变送器、温度元件这类不理想的仪表，因为对我来说，这些不像其他一些事项那样一目了然。 | All Steps | Open |  | Engineering / Hongjie Guo Production / Junfeng Zhang 工程/郭宏杰 生产/张俊峰 | QA / Mingzhi Chen QA/陈明志
37 | BLA | For equipment and piping gaps not remediated before production, establish direct traceability in cleaning documentation, including manual cleaning, targeted inspection, and cleaning or draining instructions for dead legs | Prior to Pre-PPQ | Med > 1 week < 1 Month | step1: 10/07/2026 step2: 10/20/2026 step3A: 11/09/2026 step3B: 11/28/2026 | -- | -- | -- | JOB: Update cleaning risk assessment JOB：更新清洁风险评估。 | All Steps | Open |  | Production / Anyao Tang 生产/唐安垚 | QA / Weijiang Liu QA/刘维江
38 | BLA/technical | Purified Water header throughout the facility does not meet industry guidance - sample point is not representative of POU, no means of pre-use flushing/blowing, etc. Additionally, POU filtration should be provided for any PW supplied to a growth promoting solution via hose connection (upstream of drain line). These filters should have time in use tracked and be replaced frequently (NMT 24 hours). Implement point-of-use flushing directly to waste and post-use draining and drying for purified-water lines using zero-static valves or minimum-distance tees without creating dead legs 全厂纯化水（Purified Water） | Prior to Pre-PPQ | High > 1 month | Lead time: 6 weeks Modification: 3 weeks Passivation: 1 week Validation: 4 weeks 01/05/2027 | Temporary hoses are used to connect water outlets to the points of use. | -- | -- | Please clarify if there are similar gaps on Step 1/Step 2 for any process or cleaning water supply. Also, please update us on status of modifications via videos. Also, please confirm if we can have an interim solution in place while waiitng on zero-static valves (use of hoses/portable flow meters, use of just minimum distance tees/normal valves, etc.). Need to understand what our risk mitigations will be until long term modification can be in place. 请说明 Step 1/Step 2 的工艺用水或清洁用水供应是否存在类似差距。 另外，请通过视频向我们更新改造进展。还请确认在等待零死角阀期间能否先采用临时方案（使用软管/便携式流量计，或仅使用最短距离三通/普通阀门等）。我们需要了解在长期改造到位之前将采取哪些风险缓解措施。 | All Steps | Open |  | Production / Chunpeng Hu Engineering / Hongjie Guo 生产/胡春鹏 工程/郭宏杰 | QA / Mingzhi Chen QA/陈明志
39 | BLA | Install point-of-use filters for purified water supplied by hose to growth-promoting solutions, track time in use, and replace filters no later than 24 hours | Prior to Pre-PPQ | Med > 1 week < 1 Month | 2026-10-20 | No requirement for filtration of purified water supplied by hose. | Add filtration and filter replacement-interval requirements to the MOR. | -- | AJM: Just to confirm, we only require these filters downstream of water hose connection if we are feeding a growth promoting solution. AJM：再确认一下：只有在向促进微生物生长的溶液中加水时，我们才要求在水管连接处下游安装这些过滤器。 | Purification | Open |  | Production / Chunpeng Hu 生产/胡春鹏 | QA / Qi Wang QA/王琪
40 | BLA | Assess representative sampling from new point-of-use drains and determine whether formal revalidation or an informal verification study is required to confirm water-system quality | Prior to Pre-PPQ | High > 1 month | Lead time: 6 weeks Modification: 3 weeks Passivation: 1 week Validation: 4 weeks 01/05/2027 | Temporary hoses are used to connect water outlets to the points of use. | -- | Completing this before Pre-PPQ is tight. Could it be completed after PPQ, with water used per the current practice in the meantime? | AJM: See comment above. We will need to understand what the interim solution will look like and what data we can generate closer to client in the short term (abbreviated validation/ad hoc sampling protocol, etc.). AJM：见上方意见。我们需要了解临时方案的具体形式，以及短期内能在更贴近使用端的位置产生哪些数据（简化验证/专项取样方案等）。 | All Steps | Open |  | Production / Chunpeng Hu 生产/胡春鹏 | QA / Mingzhi Chen QA/陈明志
41 | BLA | Provide Lilly with the changeover strategy and governance for reused equipment, including cleaning limits, normally uncleaned lines, soft and hard-to-clean components, and replacement of filters, membranes, and resins | Prior to Pre-PPQ | Med > 1 week < 1 Month | 2026-10-30 | Equipment is disassembled for cleaning, and ARL performs Level 2 testing of the reflux solvent. The line from the activation tank to the synthesizer is reused after solvent flushing. | We will provide current practice to Lilly's team for discussion. | -- | AJM: Please advise when this will be provided for our review and comment. We want to make sure anything that is being re-used for our process (not new) is adequately changed over/cleaned/replaced - could you provide a list for each step clarifying what equipment has been previously used by a different process? AJM：请告知何时可提供给我们审阅并提出意见。我们希望确保本工艺中所有重复使用（非新购）的设备都已充分完成换产/清洁/更换。能否按步骤提供一份清单，说明哪些设备曾用于其他工艺？ | All Steps | Open |  | Production / Yanlong Li Fan Wang Linchong Liu 生产/李延龙 王帆 刘林冲 | QA / Zhiqiang Sun QA/孙志强
42 | BLA/technical | Define and document release controls for new equipment that demonstrate removal of fabrication and construction residues, debris and particulates, and acceptable bioburden before production use | Prior to Pre-PPQ | Med > 1 week < 1 Month | 2026-10-30 | -- | We will provide current practice to Lilly's team for discussion. | -- | AJM: Please advise when this will be provided for our review. AJM：请告知何时可提供给我们审阅。 | All Steps | Open |  | Production / Yanlong Li Kai Liu 生产/李延龙 刘恺 | QA / Zhiqiang Sun QA/孙志强
43 | BLA/technical | Execute spray coverage testing for all product-contact and growth-promoting equipment and incorporate qualified pressure, time, alarm limits, flow durations, and manual cleaning or swabbing of hard-to-clean areas into operating instructions | Prior to Pre-PPQ | Med > 1 week < 1 Month | Option 1: No CIP. Equipment connections meet 2D requirement; transfer piping section does not meet 3D requirement. Disassembly cleaning will be required afterwards. Completion date: 12/17/2026 Option 2: No CIP. Equipment connections meet 2D requirement with CIP ports reserved. Most of the transfer piping meets 2D requirement and minimum 3D requirement. Completion date: 01/20/2027 Option 3: In-line CIP. The vessel and piping are designed entirely following the 2D design philosophy. Completion date: 04/25/2027 | Spray coverage testing is performed on the equipment. | Spray coverage verification will be added after the modification is completed. | -- | AJM: Please ensure that results of spracy coverage are directly incorporated into cleaning records/SOPs (time, pressure, swab locations, etc.). AJM：请确保将喷淋覆盖测试结果（时间、压力、擦拭取样位置等）直接纳入清洁记录/SOP。 | All Steps | Open |  | Production / Yanlong Li 生产/李延龙 | QA / Meijia Liu QA/刘美佳
44 | BLA | Determine and implement a means for visitors/support staff to wear a dedicated base layer in classified areas | Post PPQ | High > 1 month | 2026-12-10 | Asymchem has an internal gowning procedure for classified areas. The gowning procedure needs to be revisited. | Update the gowning procedure for classified areas. | -- | No additional follow up. 无需进一步跟进。 | All Steps | Open | Follow up with Marie to understand acceptability. | Production / Kai Liu 生产/刘恺 | QA / Zhiqiang Sun QA/孙志强
45 | BLA | Provide Lilly with the operations access-control strategy and governance, including required training, approval criteria, and periodic roster review to remove or flag inappropriate access | Post PPQ | Med > 1 week < 1 Month | 2026-11-10 | Asymchem has an internal procedure for access control. Asymchem 已有门禁控制内部程序。 | Present the Asymchem access-control procedure to Lilly. 向 Lilly 介绍 Asymchem 门禁控制程序。 | -- | AJM: Please advise when procedure will be provided. AJM：请告知何时提供该程序。 | All Steps | Open |  | Production / Kai Liu 生产/刘恺 | QA / Meijia Liu QA/刘美佳
46 | BLA | Conduct hold-time studies for all portable vessels used for temporary water or growth-promoting solution storage, confirm complete drainability, and incorporate hold-time and draining requirements into operating documents. | Prior to Pre-PPQ | Med > 1 week < 1 Month | 2026-10-05 |  | This part of work has been completed. The documents will be presented to Lilly. | -- |  | All Steps | Completed | Limit refresh time to 48 hours, even if hold time is demonstrated to be longer. | R&D / Xinyi Zhu Production / Hui Ma 研发/朱新义 生产/马辉 | QA / Qi Wang QA/王琪
47 | Technical | Define controls that ensure only acceptable mobile phase is supplied to the process and specify the system response to out-of-range temperature, composition, or pH | Prior to Pre-PPQ | Low < 1 week | 2026-10-20 | Conductivity is monitored downstream of the solution-preparation mixer: acceptable mobile phase is routed to the mobile-phase tank, and out-of-range mobile phase is diverted to waste. Solution preparation is metered by mass flow meters, so temperature changes have little effect on the metered composition before mixing. pH probes are installed at the mixer and on the receiving mobile-phase tank for monitoring. | Please refer to the slides ( link in Column L) | -- | AJM: I will review provided information and revert back. AJM：我会审阅所提供的信息后再回复。 | Purification | Open | Asymchem_Visit_Action_Tracker_Partial Feedback_09-29-2026.pptx | Production / Linchong Liu IEPE / Zhiheng Wang 生产/刘林冲 IEPE/王志恒 | QA / Meijia Liu QA/刘美佳
48 | BLA/technical | Provide the final pre-use and post-use filter integrity testing strategy | Prior to Pre-PPQ | Med > 1 week < 1 Month | 2026-10-20 | Asymchem has an internal procedure for filter integrity testing. | Present the Asymchem filter integrity testing strategy to Lilly. | -- | AJM: Please advise when strategy will be provided. AJM：请告知何时提供该策略。 | Purification | Open |  | Production / Yonggang Shi 生产/史永钢 | QA / Qi Wang QA/王琪
49 | Technical | Confirm AFD stroke height prevents blades from being submerged during displacement washes | Prior to Demo | Low < 1 week | 2026-09-30 | -- | Calculation shall be performed based on material volume and compared against the lifting height. Please refer to the slides ( link in Column L) | -- | AJM: I will review provided information and revert back. AJM：我会审阅所提供的信息后再回复。 | Purification | Open | Asymchem_Visit_Action_Tracker_Partial Feedback_09-29-2026.pptx | Production / Yanlong Li 生产/李延龙 | N/A
50 | Technical | Define the mill operating strategy for final drug-substance sampling, inerting, target drum weight without overfill, screen-temperature monitoring, and operator ergonomics | Prior to Demo | Med > 1 week < 1 Month | 2026-09-27 | -- | Provide storyboard ppt | -- |  | Purification | Completed |  | Production / Yanlong Li 生产/李延龙 | N/A
51 | BLA/technical | Store hose ends at least 6 inches off the floor and provide a clear visual indicator confirming compliant storage position | Prior to Pre-PPQ | Med > 1 week < 1 Month | 2026-10-04 | No requirement for the height of purified water hose ends above the floor. | Update the SOP to add a minimum height requirement of 6 inches. | -- | AJM: Confirm visual indicator of 6 inches will be provided in field at sotrage locations (painted line, etc.). AJM：请确认将在现场存放位置设置 6 英寸高度的目视标识（如涂刷标线等）。 | Purification | Open |  | Production / Chunpeng Hu 生产/胡春鹏 | QA / Xiong Xiong QA/熊熊
52 | BLA/technical | Require contained devices for all solids-charging operations to prevent residual powder exposure to rooms and personnel. Require split valve charging strategy for all steps (including SPPS and cleavage). | Prior to Pre-PPQ | Med > 1 week < 1 Month | 2026-11-30 | -- | Purchased SBV, and will use SBV for all solids-charging operations |  | Based on timeline provided, does this mean we will plan to start PPQ without these present? JOB: Cleaning Documation updates will be necessary for SBV additions, MOR operation instructions updates, 按所提供的时间表，这是否意味着我们计划在这些装置尚未到位的情况下开始 PPQ？ JOB：增加 SBV 需要相应更新清洁文件、更新 MOR 操作指令， | All Steps | Open |  | Production / Yanlong Li 生产/李延龙 | N/A
53 | BLA | Walk down all lines containing diaphragm valves, verify correct installation angle for drainability, and correct noncompliant installations | Prior to Pre-PPQ | Med > 1 week < 1 Month | Option 1: No CIP. Equipment connections meet 2D requirement; transfer piping section does not meet 3D requirement. Disassembly cleaning will be required afterwards. Completion date: 12/17/2026 Option 2: No CIP. Equipment connections meet 2D requirement with CIP ports reserved. Most of the transfer piping meets 2D requirement and minimum 3D requirement. Completion date: 01/20/2027 Option 3: In-line CIP. The vessel and piping are designed entirely following the 2D design philosophy. Completion date: 04/25/2027 | -- | Redesign is in progress. Once the design is confirmed, the key items will be discussed with the Lilly team before execution. |  | AJM: Not following response here. This is just simple action to correct diaphragm valves already existing. AJM：没看明白这里的回复。这只是纠正现有隔膜阀的一个简单动作。 | All Steps | Open |  | Engineering / Hongjie Guo 工程/郭宏杰 | QA / Mingzhi Chen QA/陈明志
54 | Technical | Ensure representative sampling capability exists for every required process sample while minimizing product loss | Prior to Pre-PPQ | Low < 1 week | 2026-10-25 | -- | Install a sampling valve on the 100 L preparation drums. | -- | AJM: Not following response. I would expect to see a sample map for the process (listing every sample to be pulled) and then confirmation that sampling capability exists - from where will you pull that sample (valve ID, location). AJM：没看明白这个回复。我希望看到一份该工艺的取样图（列出每一个需要取的样品），然后确认具备相应的取样能力——即每个样品将从哪里取（阀门编号、位置）。 | Purification | Open |  | Engineering / Hongjie Guo Production / Yanlong Li 工程/郭宏杰 生产/李延龙 | QA / Qi Wang QA/王琪
55 | BLA/technical | Update calibration instructions to keep tanks capped while non-retractable pH probes are calibrated, and evaluate replacement with retractable probe housings | Prior to Pre-PPQ | Med > 1 week < 1 Month | 2026-12-07 |  | Retractable pH purchased, install once arrival. Leadtime 8 weeks. |  | AJM: What will be interim solution for PPQ since this installation will have to occur after PPQ start? AJM：既然该安装只能在 PPQ 开始后进行，PPQ 期间的临时方案是什么？ | Purification | Open |  | Production / Yanlong Li 生产/李延龙 | QA / Mingzhi Chen QA/陈明志

## Sheet1
Category | Implementation Timing | Implementation Effort | Scope
BLA | Prior to Pre-PPQ | Low < 1 week | All Steps
Technical | Prior to Demo | Med > 1 week < 1 Month | SPPS
BLA/technical | Post PPQ | High > 1 month | Cleavage
Impurity Investigation |  |  | Purification

## Summary
BLA Visit Action Tracker Summary BLA 来访行动项跟踪汇总
Metric 指标 | Count 数量 | Priority 优先级 | Count 数量
Total Actions 行动项总数 | 55 | High 高 | 9
High Priority 高优先级 | 9 | Medium 中 | 31
Open 未关闭 | 51 | Low 低 | 15
In Progress 进行中 | 0
Blocked 阻塞 | 0
Completed 已完成 | 4

## Instructions (hidden)
How to Use This Tracker 本跟踪表使用说明
• Assign a named owner in the Suggested Owner column, replacing the suggested function if appropriate. • 在建议负责人一栏指定具体责任人；如适用，替换建议的职能。
• Set a due date for every High-priority item. • 为每个高优先级事项设定截止日期。
• Use the Status dropdown to update progress. • 使用“状态”下拉列表更新进展。
• Use table filters to review actions by day, area, priority, owner, or status. • 使用表格筛选，按日期、区域、优先级、责任人或状态查看行动项。
• Priorities and owners are suggested organizational fields derived from the visit notes and should be confirmed by the project team. • 优先级与责任人为根据来访记录建议的组织字段，需由项目团队确认。